## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in GHOKSADANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000494/2021-2022 | 459/MTB | 04/03/2022 | 19/03/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.98 | 4.96 | 99.49 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing functional house hold tap connection within command area under GHOKSADANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000113/2022-2023 | 130/MTB | 23/06/2022 | 08/07/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.8 | 4.8 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Sinking of Big Dia Tubewell at GHOSKADANGA PWSS under JAL JEEVAN MISSION (Z-I: 3rd Site Z-II: HWS & 2nd Site) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000389/2022-2023 | 1034/CD | 29/09/2022 | 28/11/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 35.04 | 23.33 | 66.59 | 30
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing FHTC and Laying of Pipe line at GHOSKADANGA PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000351/2022-2023 | 3004/CD | 29/09/2022 | 29/10/2022 | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 30.7 | 14 | 45.6 | 48
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing FHTC and laying of pipe line at GHOKSADANGA PWSS under Jal Jeevan Mission (Part-Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000889/2022-2023 | 1001/CD | 29/09/2022 | 29/10/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 30.71 | 14.6 | 47.53 | 48
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOKSADANGA ZONE - I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1210/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000537/2022-2023 | 1780/CD | 02/03/2023 | 15/01/2026 | Z STAR COMMOTRADE PVT LTD | 779.99 | 488.4 | 62.62 | 56
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOSKADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000780/2022-2023 | 1696/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 7.64 | 7.64 | 100 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing FHTC and Laying of Pipe line at GHOSKADANGA PWSS under JAL JEEVAN MISSION (PART -Y) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000775/2022-2023 | 1662/CD | 10/02/2023 | 11/04/2023 | SWAPAN SAHA | 30.71 | 14.59 | 47.52 | 48
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GHOKSADANGA water supply scheme, TW no III,IV AND V under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000885/2023-2024 | 2426/NMD-II | 10/08/2023 | 01/09/2025 | QUAZI NOZRUL ISLAM | 34.2 | 0 | 0 | 80
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOKSADANGA ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1243/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000557/2022-2023 | 1782/CD | 02/03/2023 | 15/01/2026 | Z STAR COMMOTRADE PVT LTD | 638.51 | 346.96 | 54.34 | 50
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOSKADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000368/2023-2024 | 1391/CD | 05/12/2023 | 08/04/2025 | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 31.96 | 16.04 | 50.18 | 50
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 180/CD | 27/04/2023 | 27/04/2023 | Resource Division | 43.99 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO GHOKSADANGA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000555/2024-2025 | 2240/CD | 23/12/2024 | 21/02/2025 | Z STAR COMMOTRADE PVT LTD | 40.4 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO GHOKSADANGA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000581/2024-2025 | 2264/CD | 23/12/2024 | 21/02/2025 | Z STAR COMMOTRADE PVT LTD | 34.63 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO RAMTHANGA GHOKSADANGA SALMARA PRATHAM KHANDA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000528/2024-2025 | 2212/CD | 23/12/2024 | 21/02/2025 | SUBHAS CHANDRA ROY | 60.24 | 0 | 0 | 50
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part G | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000584/2023-2024 | 600/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 54.64 | 24.55 | 44.93 | 100
18 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA PWSS ZONE-II TW I |  |  | BILL/02762/2023-2024 | BP-2023-24-631 | 22/02/2024 | 22/02/2024 | WBSEDCL | 7.85 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA PWSS ZONE-I TW I |  |  | BILL/02761/2023-2024 | BP-2023-24-632 | 22/02/2024 | 22/02/2024 | WBSEDCL | 3.66 | 0 | 0 | 0
20 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA TW II ZONE-II. |  |  | BILL/00754/2024-2025 | BP-216/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.49 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Aug. of Ghokshadanga Water Supply Scheme Zone-II of TW No.- I and II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/001227/2024-2025 | 844/NMD-II | 11/03/2025 | 10/04/2025 | M/S SAJAHAN CHOWDHURY | 23.51 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000269/2025-2026 | 745/CD | 17/05/2025 | 15/08/2025 | GHOSH AND SAHA CONSTRUCTION | 59.92 | 0 | 0 | 0
Total | [13 empty] | 21752.83 | 959.86 | 4.41