## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Supply of different Computer Peripherals for Officials used under Cooch Behar Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000272/2022-2023 | 874/CD | 21/09/2022 | 28/09/2022 | CYBERNET | 0.8 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Supply of different Computer Peripherals for Officials used under Cooch Behar Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000273/2022-2023 | 875/CD | 21/09/2022 | 28/09/2022 | CYBERNET | 0.77 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC & Laying of Pipe line of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ?Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000322/2022-2023 | 931/CD | 26/09/2022 | 25/11/2022 | ASHIM KUMAR CHAKRABORTY | 99.15 | 85.94 | 86.67 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Pipe Line in the Command area incl. Providing House connection at PURBADHULIA BALDIHATI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000114/2021-2022 | 303/CD | 13/08/2021 | 12/10/2021 | SAMBHU BANIK | 40.7 | 4 | 9.82 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Extension work for Hiring of Diesel Vehicle of Bolero Maxi cab for the Office use of Assistant Engineer, RWS Cooch Behar Sub-Division, PHE Dte. f04 Months (October 2022 to January 2023). | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000270/2022-2023 | 821/CD | 13/09/2022 | 13/01/2023 | AJAD HOSSAIN | 0.67 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC Construction of B/Wall and Laying of Pipe line at 2nd Site of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ¿T) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000261/2022-2023 | 762/CD | 02/09/2022 | 01/11/2022 | KHOKAN DAS | 82.18 | 75.62 | 92.01 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC & Lay0ing of Pipe line of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ¿W) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000262/2022-2023 | 763/CD | 02/09/2022 | 01/11/2022 | M/S KAMAK ENGINEERS AND CO | 75.53 | 73.33 | 97.09 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC & Laying of Pipe line of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ¿V) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000264/2022-2023 | 766/CD | 02/09/2022 | 01/11/2022 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 75.6 | 73.41 | 97.1 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC and Laying of Pipe line at HW Site of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ¿Q) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000320/2022-2023 | 929/CD | 26/09/2022 | 25/11/2022 | SWAPAN SAHA | 68.56 | 68.52 | 99.93 | 1
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC Construction of Pump House and Laying of Pipe line at 2nd Site of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ?S) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000332/2022-2023 | 981/CD | 29/09/2022 | 28/11/2022 | ASHIT KUMAR SINGHA | 83.14 | 75.55 | 90.87 | 1
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC and Laying of Pipe line at HW Site of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ¿P) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000326/2022-2023 | 975/CD | 29/09/2022 | 28/11/2022 | BIJOY ROY | 68.41 | 65.62 | 95.93 | 1
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Purba Dhuliabaldihati Water Supply Scheme TWNo- IV under NMD-II,PHE.Dte,APD |  |  | ORD/001182/2023-2024 | 2912/NMD-II | 31/10/2023 | 30/11/2023 | PRAGATI CONSTRUCTION COMPANY | 10.86 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC & Laying of Pipe line of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ?X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000324/2022-2023 | 973/CD | 29/09/2022 | 28/11/2022 | SANJAY MANDAL | 52.11 | 49.97 | 95.89 | 1
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 101/CD | 26/04/2023 | 26/04/2023 | Resource Division | 5.95 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | UPLOAD CHARGES (MOBILE APPS) |  |  | BILL/00548/2023-2024 | BP-16,29,31-37 | 17/04/2023 | 17/04/2023 | BIPASHA MAHANTA BANIK | 8.86 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | supply of fuel at TFG SUB DIVN PHED |  |  | BILL/00731/2023-2024 | BP-559 | 11/10/2023 | 11/10/2023 | SUCHITRO FUEL STATION | 0.55 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Execution of different works related to PWSS under JAL JEEVAN MISSION |  |  | ORD/000765/2023-2024 | 12 | 24/11/2023 | 23/01/2024 | DIGENDRA CH DEY & SONS | 0.01 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC Repairing of Pump House & B/Wall and Laying of Pipe line at HW Site of PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION (PART ?R) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000334/2022-2023 | 983/CD | 29/09/2022 | 28/11/2022 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 73.17 | 72.3 | 98.8 | 100
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Execution of different works related to PURBA DHULIA BALDIHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000519/2022-2023 | 1606/CD | 03/02/2023 | 03/07/2023 | SHRI ANNAPURNA DISTRIBUTORS | 226.02 | 224.34 | 99.26 | 100
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION FOR PURBBA DHULIA BALDIHATI PIPED WATER SUPPLY SCHEME | SM/11983 | Augmentation | Providing FHTC and Laying of pipe line and other allied work at PURBA FULKARDABRI PWSS under JAL JEEVAN MISSION (Part-D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000329/2022-2023 | 978/CD | 29/09/2022 | 16/05/2025 | MANABENDRA DE | 76.88 | 0 | 0 | 1
Total | [13 empty] | 1049.93 | 868.59 | 82.73