## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line of PANIGRAM ZONE ¿I I PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000333/2022-2023 | 982/CD | 29/09/2022 | 28/11/2022 | KAMIRUL SK AND CO | 83.88 | 0 | 0 | 1
2 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Sinking of Big Dia Tubewell at HWSite & 2nd Site of PANIGRAM ZONE ¿ I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000378/2022-2023 | 799/CD | 09/09/2022 | 08/11/2022 | S DUTTA | 23.36 | 0 | 0 | 1
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of B/Wall HW Site of PANIGRAM ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000380/2022-2023 | 801/CD | 09/09/2022 | 08/11/2022 | AMBITIOUS ENTERPRISE | 76.11 | 0 | 0 | 78
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000050/2023-2024 | 498/CD | 05/06/2023 | 05/07/2023 | SANJAY MANDAL | 2.27 | 0 | 0 | 100
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Sinking of Big Dia Tubewell at HWSite & 2nd Site of PANIGRAM ZONE ¿ I I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000330/2022-2023 | 979/CD | 29/09/2022 | 29/10/2022 | KAMIRUL SK AND CO | 24.61 | 0 | 0 | 1
6 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM TW-II Z-II |  |  | BILL/00014/2023-2024 | BP-2023-24-87 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM W/SS TW I,Z-II |  |  | BILL/00020/2023-2024 | BP-2023-24-89 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM W/SS TW I,Z-I |  |  | BILL/00018/2023-2024 | BP-2023-24-90 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM W/SS TW II,Z-I |  |  | BILL/00019/2023-2024 | BP-2023-24-88 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house HW Site of PANIGRAM ZONE - II PWSS under JAL JEEVAN MISSION (PART ¿Y) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000383/2022-2023 | 802/CD | 09/09/2022 | 08/11/2022 | JAI BHARAT COMERCIAL CORPORATION | 69.76 | 0 | 0 | 90
11 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house HW Site of PANIGRAM ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000384/2022-2023 | 803/CD | 09/09/2022 | 08/11/2022 | MADHAB SAHA | 63.13 | 0 | 0 | 1
12 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line of PANIGRAM ZONE ¿ I PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000391/2022-2023 | 1035/CD | 29/09/2022 | 28/11/2022 | S DUTTA | 76.88 | 0 | 0 | 35
13 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house 2ND Site of PANIGRAM ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿P) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000336/2022-2023 | 985/CD | 29/09/2022 | 28/11/2022 | SASANKA ROY | 63.91 | 0 | 0 | 80
14 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION ZIPART F | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000116/2023-2024 | 639/CD | 12/07/2023 | 10/09/2023 | HIGHLIFE INTERNATIONAL | 85.61 | 0 | 0 | 87
15 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION ZIIPART F | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000098/2023-2024 | 638/CD | 12/07/2023 | 10/09/2023 | M/S T R PARIK | 98.15 | 0 | 0 | 83
16 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | EXECUTION OF DIFFERENT WORKS RELATED TO RAMTHANGA PANIGRAM BARAIBARI PWSS UNDER JAL JEEVAN MISSION. MTB |  |  | ORD/000539/2024-2025 | 2223/CD | 23/12/2024 | 21/02/2025 | SHREE RANI SATI ENTERPRISE | 41.72 | 0 | 0 | 0
17 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 32/CD | 05/01/2024 | 05/01/2024 | Resource Division | 31.83 | 0 | 0 | 0
18 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | FUEL BILL |  |  | BILL/02020/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 1.68 | 0 | 0 | 0
19 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | FUEL BILL |  |  | BILL/02076/2023-2024 | BP-1409 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.68 | 0 | 0 | 0
20 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | HIRING VEHICLE FOR AE/SD |  |  | BILL/00488/2024-2025 | BP-215 | 31/07/2024 | 31/07/2024 | PARAUDDIN MIA | 0.55 | 0 | 0 | 0
21 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000522/2022-2023 | 1609/CD | 03/02/2023 | 22/02/2025 | M/S T R PARIK | 341.24 | 0 | 0 | 90
22 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
23 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM Z- II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000510/2023-2024 | 307/CD | 09/02/2024 | 03/02/2025 | M/S T R PARIK | 71.05 | 0 | 0 | 60
24 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM Z- II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000520/2023-2024 | 318/CD | 09/02/2024 | 03/02/2025 | M/S T R PARIK | 85.44 | 0 | 0 | 60
25 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Supply & delivery of Submersible pump motor set and other Electro Mechanical Componenets at PAKHIHAGA (REJU) PWSS and adjacent W/S Scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000040/2024-2025 | 1932/CMSD | 13/06/2024 | 01/04/2025 | B.B CONCERNED | 4.54 | 0 | 0 | 100
26 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | EXECUTION OF DIFFERENT WORKS (within PANIGRAM & BARA GOPALPUR area) RELATED TO KHARIJA KHAWARDARA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000659/2024-2025 | 88/CD | 17/01/2025 | 18/03/2025 | GOUTAM KUMAR DAS | 57.5 | 0 | 0 | 0
27 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to (within CK KHAGRABARI) PANIGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000022/2024-2025 | 1130/CD | 14/06/2024 | 13/08/2024 | BIJOY ROY | 43.7 | 0 | 0 | 50
28 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000059/2025-2026 | 695/CD | 16/05/2025 | 12/11/2025 | M/S JAYA SARKAR | 12.09 | 0 | 0 | 65
29 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
30 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house 2ND Site of PANIGRAM ZONE - I I PWSS under JAL JEEVAN MISSION (PART ¿R) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000386/2022-2023 | 804/CD | 09/09/2022 | 25/02/2025 | DULAL MAJUMDER | 63.23 | 0 | 0 | 100
31 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of B/Wall HW Site of PANIGRAM ZONE - II PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000379/2022-2023 | 800/CD | 09/09/2022 | 23/10/2025 | JAL PRAVAHIKA PVT. LTD. | 82.78 | 0 | 0 | 90
32 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Panigram water supply scheme, TW no I,II,III and IV under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000888/2022-2023 | 736/NMD-II | 31/03/2023 | 31/07/2024 | S.P ENTERPRISE (SLG) | 43.53 | 0 | 0 | 100
Total | [13 empty] | 21411.06 | 0 | 0