## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Sinking of Big Dia Tubewell at HWSite & 2nd Site of PANIGRAM ZONE ¿ I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000378/2022-2023 | 799/CD | 09/09/2022 | 08/11/2022 | S DUTTA | 23.36 | 23.26 | 99.55 | 1
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line of PANIGRAM ZONE ¿I I PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000333/2022-2023 | 982/CD | 29/09/2022 | 28/11/2022 | KAMIRUL SK AND CO | 83.88 | 73.87 | 88.07 | 1
3 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house HW Site of PANIGRAM ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000384/2022-2023 | 803/CD | 09/09/2022 | 08/11/2022 | MADHAB SAHA | 63.13 | 46.53 | 73.71 | 1
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Sinking of Big Dia Tubewell at HWSite & 2nd Site of PANIGRAM ZONE ¿ I I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000330/2022-2023 | 979/CD | 29/09/2022 | 29/10/2022 | KAMIRUL SK AND CO | 24.61 | 24.54 | 99.71 | 1
5 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM TW-II Z-II |  |  | BILL/00014/2023-2024 | BP-2023-24-87 | 15/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM W/SS TW I,Z-I |  |  | BILL/00018/2023-2024 | BP-2023-24-90 | 15/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM W/SS TW II,Z-I |  |  | BILL/00019/2023-2024 | BP-2023-24-88 | 15/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PANIGRAM W/SS TW I,Z-II |  |  | BILL/00020/2023-2024 | BP-2023-24-89 | 15/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of B/Wall HW Site of PANIGRAM ZONE - II PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000379/2022-2023 | 800/CD | 09/09/2022 | 08/11/2022 | JAL PRAVAHIKA PVT. LTD. | 82.78 | 65.93 | 79.65 | 18
10 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000050/2023-2024 | 498/CD | 05/06/2023 | 05/07/2023 | SANJAY MANDAL | 2.27 | 2.16 | 94.95 | 100
11 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of B/Wall HW Site of PANIGRAM ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000380/2022-2023 | 801/CD | 09/09/2022 | 08/11/2022 | AMBITIOUS ENTERPRISE | 76.11 | 59.9 | 78.7 | 78
12 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Panigram water supply scheme, TW no I,II,III and IV under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000888/2022-2023 | 736/NMD-II | 31/03/2023 | 30/04/2023 | S.P ENTERPRISE (SLG) | 43.53 | 14.82 | 34.06 | 30
13 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 32/CD | 05/01/2024 |  | Resource Division | 31.83 | 0 | 0 | 0
14 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house 2ND Site of PANIGRAM ZONE - I PWSS under JAL JEEVAN MISSION (PART ¿P) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000336/2022-2023 | 985/CD | 29/09/2022 | 28/11/2022 | SASANKA ROY | 63.91 | 54.35 | 85.05 | 80
15 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION ZIIPART F | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000098/2023-2024 | 638/CD | 12/07/2023 | 10/09/2023 | M/S T R PARIK | 98.15 | 80.58 | 82.1 | 83
16 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION ZIPART F | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000116/2023-2024 | 639/CD | 12/07/2023 | 10/09/2023 | HIGHLIFE INTERNATIONAL | 85.61 | 84 | 98.12 | 87
17 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000522/2022-2023 | 1609/CD | 03/02/2023 | 03/07/2023 | M/S T R PARIK | 341.24 | 167.59 | 49.11 | 45
18 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM Z- II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000510/2023-2024 | 307/CD | 09/02/2024 | 09/04/2024 | M/S T R PARIK | 71.05 | 0 | 0 | 0
19 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to PANIGRAM Z- II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000520/2023-2024 | 318/CD | 09/02/2024 | 09/04/2024 | M/S T R PARIK | 85.44 | 0 | 0 | 0
20 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | FUEL BILL |  |  | BILL/02020/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 1.68 | 0 | 0 | 0
21 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | FUEL BILL |  |  | BILL/02076/2023-2024 | BP-1409 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 1.68 | 0 | 0 | 0
22 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house 2ND Site of PANIGRAM ZONE - I I PWSS under JAL JEEVAN MISSION (PART ¿R) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000386/2022-2023 | 804/CD | 09/09/2022 | 08/11/2022 | DULAL MAJUMDER | 63.23 | 55.75 | 88.18 | 30
23 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line of PANIGRAM ZONE ¿ I PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000391/2022-2023 | 1035/CD | 29/09/2022 | 28/11/2022 | S DUTTA | 76.88 | 60.11 | 78.18 | 35
24 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Providing FHTC and Laying of Pipe line & Construction of Pump house HW Site of PANIGRAM ZONE - II PWSS under JAL JEEVAN MISSION (PART ¿Y) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000383/2022-2023 | 802/CD | 09/09/2022 | 08/11/2022 | JAI BHARAT COMERCIAL CORPORATION | 69.76 | 9.2 | 13.18 | 90
25 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Supply & delivery of Submersible pump motor set and other Electro Mechanical Componenets at PAKHIHAGA (REJU) PWSS and adjacent W/S Scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000040/2024-2025 | 1932/CMSD | 13/06/2024 | 13/07/2024 | B.B CONCERNED | 4.54 | 0 | 0 | 0
26 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Execution of different works related to (within CK KHAGRABARI) PANIGRAM PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000022/2024-2025 | 1130/CD | 14/06/2024 | 13/08/2024 | BIJOY ROY | 43.7 | 0 | 0 | 0
27 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
28 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | PANIGRAM PIPED WATER SUPPLY SCHEME | SM/12271 | New | HIRING VEHICLE FOR AE/SD |  |  | BILL/00488/2024-2025 | null | 01/06/2024 |  | PARAUDDIN MIA | 0.55 | 0 | 0 | 0
Total | [13 empty] | 21232.22 | 822.59 | 3.87