## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 1383/CD | 22/12/2022 | 22/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 1369/CD | 22/12/2022 | 22/12/2022 | Resource Division | 205.68 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Sinking of Big Dia Tubewell at CHAKIAR CHHARA PWSS under JAL JEEVAN MISSION (Z-II: 3rd Site Z-III: HWS & 2nd Site) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000381/2022-2023 | 832/CD | 14/09/2022 | 13/11/2022 | AKANSHA COMMERCIAL PVT. LTD. | 35.11 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Sinking of Big Dia Tubewell at HWSite & 2nd Site of CHAKIAR CHHARA ZONE - I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000385/2022-2023 | 834/CD | 14/09/2022 | 13/11/2022 | AKANSHA COMMERCIAL PVT. LTD. | 23.41 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing FHTC & Construction of Boundary Wall at 3RD T/W site and laying of Pipe line and other allied works at CHAKIAR CHHARA ZONE - II PWSS Under Cooch Behar division P.H.E.Dte.(Part-X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000288/2022-2023 | 831/CD | 14/09/2022 | 13/11/2022 | NABIN DEBNATH | 91.36 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing functional house hold tap connection within command area under CHEKIARCHHARA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000128/2022-2023 | 123/MTB | 23/06/2022 | 08/07/2022 | PINAKI SAHA | 4.79 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing fire hydrant at head work complex along with platform and refitting over flow line of OHR and other allied works related to pipe line under Chekichhara PWSS under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000578/2021-2022 | 170/MTB | 01/09/2021 | 16/09/2021 | PINAKI SAHA | 4.27 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Reconstruction of boundary wall at 2nd tube well site under Chekichhara PWSS under Mathabhanga Sub-division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000579/2021-2022 | 335/MTB | 04/01/2022 | 19/01/2022 | PINAKI SAHA | 2 | 0 | 0 | 1
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | QUOTATION FOR NEW SERVIVE CONNECTION AT CHAKIACHARA (AUG) TW NO-II,Z-III |  |  | BILL/00097/2023-2024 | BP-2023-24-38 | 10/05/2023 | 10/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHAKIACHARA (AUG) Z-III,PH NO-III |  |  | BILL/00143/2023-2024 | BP-2023-24-103 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | QUOTATION FOR NEW SERVIVE CONNECTION AT CHAKIACHARA (AUG) (H/W SITE),Z-III |  |  | BILL/00098/2023-2024 | BP-2023-24-39 | 10/05/2023 | 10/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing FHTC and Laying of pipe line, Const. Of Pump house , B/Wall at 3rd T/W site and other allied work of CHAKIAR CHHARA Z-III PWSS under JAL JEEVAN MISSION (PART ¿B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000382/2022-2023 | 833/CD | 14/09/2022 | 15/01/2025 | AKANSHA COMMERCIAL PVT. LTD. | 94.22 | 0 | 0 | 11
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing FHTC & Construction of Pumphouse at 3RD T/W site and laying of Pipe line and other allied works at CHAKIAR CHHARA ZONE - II PWSS Under Cooch Behar division P.H.E.Dte.(Part-Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000321/2022-2023 | 930/CD | 26/09/2022 | 25/11/2022 | RAJIB CHAKRABORTY | 96.18 | 0 | 0 | 40
14 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGUMENTATION OF CHEKIACHARA Water Supply Scheme TW No.- I and II OF ZONE -I TW No.- I and II OF ZONE -II TW No.- I and II OF ZONE -III under NMD-II,PHE.Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000051/2023-2024 | 1110/NMD-II | 05/06/2023 | 05/07/2023 | ORIENTAL ENGINEERING CO. | 62.78 | 0 | 0 | 65
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing FHTC & Laying of Pipe line of CHAKIAR CHHARA ZONE - II PWSS under JAL JEEVAN MISSION (PART ¿C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000327/2022-2023 | 976/CD | 29/09/2022 | 28/11/2022 | M/S. AMIT KUMAR GUPTA | 98.39 | 0 | 0 | 99
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO CHAKIACHARA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000570/2024-2025 | 2254/CD | 23/12/2024 | 21/02/2025 | M/S A. B. ENTERPRISE | 31.73 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works related to CHAKIARCHHARA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 975/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000456/2022-2023 | 1507/CD | 19/01/2023 | 18/06/2023 | SIDHARTHA ROY | 185.06 | 0 | 0 | 15
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works related to CHAKIARCHHARA (RUNIBARI) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000546/2022-2023 | 1680/CD | 13/02/2023 | 13/07/2023 | KAJAL KUMAR DE | 99.84 | 0 | 0 | 100
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works related to CHAKIARCHARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000367/2023-2024 | 1392/CD | 05/12/2023 | 03/02/2024 | M/S SURAJIT MAJUMDER | 33.08 | 0 | 0 | 21
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works related to CHAKIARCHHARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000479/2023-2024 | 282/CD | 09/02/2024 | 09/04/2024 | SIDHARTHA ROY | 39 | 0 | 0 | 30
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works related to CHAKIARCHHARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000784/2023-2024 | 665/CD | 11/03/2024 | 10/05/2024 | MATARA CONSTRUCTION CO. | 9.07 | 0 | 0 | 100
22 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Electric quotation bill for NSC at Chakiachara (Aug) PWSS Tw I Zone-II |  |  | BILL/02300/2023-2024 | BP-2023-24-488 | 21/12/2023 | 21/12/2023 | WBSEDCL | 8.62 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | PROVIDING INTERNET CONNECTION |  |  | BILL/00599/2024-2025 | BP-234 | 01/08/2024 | 01/08/2024 | BIJOY ROY | 0.1 | 0 | 0 | 0
24 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHEKIACHARA TW II ZONE-I. |  |  | BILL/00755/2024-2025 | BP-220/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.01 | 0 | 0 | 0
25 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | SHIFTING OF 2 NOS. LT PCC POLE AT 2nd SITE OF CHEKICHARA PWSS FOR REPLACEMENT OF TUBEWELL. |  |  | BILL/00281/2024-2025 | BP-79/24-25 | 15/05/2024 | 15/05/2024 | WBSEDCL | 0.52 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works related to CHEKIACHARA ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000334/2023-2024 | 1319/CD | 24/11/2023 | 17/01/2025 | RAJIB CHAKRABORTY | 81.93 | 0 | 0 | 75
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Execution of different works (Within area of DUMNIGURI) related to CHEKIACHARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000519/2023-2024 | 317/CD | 09/02/2024 | 03/02/2025 | SHREE RANI SATI ENTERPRISE | 44.92 | 0 | 0 | 45
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF CHEKIACHARA PIPED WATER SUPPLY SCHEME | SM/12371 | Augmentation | Providing FHTC & Laying of Pipe line of CHAKIAR CHHARA ZONE - II PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000325/2022-2023 | 974/CD | 29/09/2022 | 16/05/2025 | M/S JHA CONSTRUCTION | 94.25 | 0 | 0 | 95
Total | [13 empty] | 21205.38 | 0 | 0