## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DAKSHIN BAJEJAMA KHASBASH PWSS TW I |  |  | BILL/02728/2023-2024 | BP-2023-24-603 | 15/02/2024 | 15/02/2024 | WBSEDCL | 5.86 | 0 | 0 | 0
2 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | ELECTRIC QUOTATION BILL FOR NSC AT DAKSHIN BAJEJAMA KHASBAS TW NO II. |  |  | BILL/01882/2024-2025 | BP-441/24-25 | 16/12/2024 | 16/12/2024 | WBSEDCL | 3.75 | 0 | 0 | 0
3 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Dakhshin Bajejama Khasbas water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000878/2023-2024 | 2461/NMD-II | 11/08/2023 | 04/09/2025 | TALUKDAR ENTERPRISE | 21.46 | 17.54 | 81.75 | 80
4 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DAKSHIN BAJEJAMA KHASBAS Dumniguru & BHOGMARA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000585/2024-2025 | 2268/CD | 23/12/2024 | 19/10/2025 | SWAPAN KUMAR ROY | 45.76 | 0 | 0 | 60
6 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | EXECUTION OF DIFFERENT WORKS RELATED TO JNANDAS & DAKSHIN BAJEJAMA KHASBAS PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000531/2024-2025 | 2215/CD | 23/12/2024 | 21/10/2025 | ASOK KUMAR DHAR | 71.16 | 0 | 0 | 30
7 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000112/2025-2026 | 731/CD | 17/05/2025 | 15/08/2025 | KAJAL KUMAR DE | 7.22 | 0 | 0 | 30
8 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Execution of different works related to DAKSHIN BAJEJAMA KHASBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000160/2023-2024 | 889/CD | 25/08/2023 | 22/09/2025 | ASOK KUMAR DHAR | 324.17 | 241.47 | 74.49 | 60
9 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Execution of different works related to DAKSHIN BAJEJAMA KHASBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000490/2023-2024 | 292/CD | 09/02/2024 | 10/05/2025 | DAS ENTERPRISE | 14.91 | 11.43 | 76.69 | 30
10 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000033/2025-2026 | 599/CD | 28/04/2025 | 27/07/2025 | SHRI ANNAPURNA DISTRIBUTORS | 23.12 | 0 | 0 | 30
Total | [13 empty] | 20306.7 | 270.44 | 1.33