## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DAKSHIN BAJEJAMA KHASBASH PWSS TW I |  |  | BILL/02728/2023-2024 | BP-2023-24-603 | 15/02/2024 |  | WBSEDCL | 5.86 | 0 | 0 | null
2 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT DAKSHIN BAJEJAMA KHASBASH PWSS TW I |  |  | BILL/02728/2023-2024 | BP-2023-24-603 | 15/02/2024 |  | WBSEDCL | 5.86 | 0 | 0 | null
3 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Execution of different works related to DAKSHIN BAJEJAMA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000490/2023-2024 | 292/CD | 09/02/2024 | 09/04/2024 | DAS ENTERPRISE | 14.91 | 0 | 0 | 0
4 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Execution of different works related to DAKSHIN BAJEJAMA KHASBAS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000160/2023-2024 | 889/CD | 25/08/2023 | 22/01/2024 | ASOK KUMAR DHAR | 324.17 | 98.67 | 30.44 | 60
5 | COOCHBEHAR | Haldibari | Coochbehar Division | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
6 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | DAKSHIN BAJEJAMA KHASBAS PIPED WATER SUPPLY SCHEME. | SM/13118 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Dakhshin Bajejama Khasbas water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000878/2023-2024 | 2461/NMD-II | 11/08/2023 | 10/09/2023 | TALUKDAR ENTERPRISE | 21.46 | 0 | 0 | 40
Total | [13 empty] | 20161.54 | 98.67 | 0.49