## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Execution of different works related to ICHAMARI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 984/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000464/2022-2023 | 1515/CD | 19/01/2023 | 12/12/2025 | ASHIM KUMAR CHAKRABORTY | 360.55 | 250.39 | 69.45 | 47
2 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Ichhamari water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000735/2023-2024 | 2319/NMD-II | 01/08/2023 | 31/08/2023 | SUMON ELECTRICAL | 21.49 | 21.26 | 98.95 | 100
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Cooch Behar-II Block (Part -B) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000239/2023-2024 | 902/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Dinhata-I Block (Part-A) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000240/2023-2024 | 903/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
5 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Dinhata-II Block (Part-A) under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000242/2023-2024 | 905/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Mathabhanga-II Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000247/2023-2024 | 910/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
7 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Haldibari Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000248/2023-2024 | 911/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
8 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Sitalkuchi Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000251/2023-2024 | 914/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Entry of yearly Data Updating (YDU) in IMIS website (Habitation wise Entry for every single habitation) at Cooch Behar Division, PHED. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000252/2023-2024 | 915/CD | 31/08/2023 | 07/09/2023 | BIPASHA MAHANTA BANIK | 0.3 | 0.3 | 100 | 100
10 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000204/2023-2024 | 527/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
11 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000205/2023-2024 | 528/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
12 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Surveying door to door to collect information regarding Jal Jeevan Mission of Mathabhanga-I Block under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000246/2023-2024 | 909/CD | 31/08/2023 | 15/09/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
13 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000206/2023-2024 | 529/CD | 21/06/2023 | 20/08/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
14 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 129/CD | 27/04/2023 | 27/04/2023 | Resource Division | 15.13 | 0 | 0 | 0
15 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | QUOTATION FOR NSC AT ICHAMARI PH NO I |  |  | BILL/01042/2023-2024 | BP-2023-24-241 | 27/07/2023 | 27/07/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
16 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | QUOTATION FOR NSC AT ICHCHAMARI BANESWAR PH NO-II,Z-II |  |  | BILL/01035/2023-2024 | BP-2023-24-243 | 27/07/2023 | 27/07/2023 | WBSEDCL | 7.86 | 0 | 0 | 0
17 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | QUOTATION FOR NSC AT ICHCHAMARI PH NO-II |  |  | BILL/01036/2023-2024 | BP-2023-24-242 | 27/07/2023 | 27/07/2023 | WBSEDCL | 5.88 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Execution of different works related to ICHAMARI PWSS under JAL JEEVAN MISSION P B |  |  | ORD/000031/2024-2025 | 1140/CD | 14/06/2024 | 13/08/2024 | ASHIM KUMAR CHAKRABORTY | 38.89 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | Execution of different works related to ICHAMARI & AMBARI PWSS under JAL JEEVAN MISSION P B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000072/2024-2025 | 1185/CD | 18/06/2024 | 16/09/2024 | ASHIM KUMAR CHAKRABORTY | 38.89 | 0 | 0 | 75
20 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | HIRING VEHICLE FOR AE RWS |  |  | BILL/02033/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 0.18 | 0 | 0 | 0
21 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | HIRING OF VEHICLE AE SADAR |  |  | BILL/02063/2023-2024 | BP-1421 | 31/03/2024 | 31/03/2024 | PARAUDDIN MIA | 0.18 | 0 | 0 | 0
22 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | HIRING VEHICLE FOR AE RWS |  |  | BILL/02066/2023-2024 | BP-1423 | 31/03/2024 | 31/03/2024 | AJAD HOSSAIN | 0.03 | 0 | 0 | 0
23 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | FUEL BILL FOR AE/TFG |  |  | BILL/02094/2023-2024 | BP-1174 | 13/03/2024 | 13/03/2024 | SUCHITRO FUEL STATION | 0.79 | 0 | 0 | 0
24 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
25 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | HIRING VEHICLE FOR AE SADAR |  |  | BILL/02067/2023-2024 | BP-1228 | 31/03/2024 | 31/03/2024 | PARAUDDIN MIA | 0.7 | 0 | 0 | 0
26 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | fuel bill |  |  | BILL/02064/2023-2024 | BP-1417 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.44 | 0 | 0 | 0
27 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | FUEL BILL FIR AE/TFG |  |  | BILL/02093/2023-2024 | BP-1173 | 13/03/2024 | 13/03/2024 | SUCHITRO FUEL STATION | 0.39 | 0 | 0 | 0
28 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | HIRING VEHICLE FOR AE RWS |  |  | BILL/02065/2023-2024 | BP-1422 | 31/03/2024 | 31/03/2024 | AJAD HOSSAIN | 0.18 | 0 | 0 | 0
29 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | FUEL BILL |  |  | BILL/02092/2023-2024 |  | 01/03/2024 | 01/03/2024 | SUCHITRO FUEL STATION | 0.39 | 0 | 0 | 0
30 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000289/2025-2026 | 79X8/CD | 23/05/2025 | 21/08/2025 | SWAPAN KUMAR ROY | 28.88 | 0 | 0 | 0
31 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | ICHAMARI PIPED WATER SUPPLY SCHEME. | SM/13119 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000283/2025-2026 | 792/CD | 23/05/2025 | 21/08/2025 | ANIMESH DHAR CHOUDHURY | 32.79 | 0 | 0 | 0
Total | [13 empty] | 621.53 | 281.78 | 45.34