## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for NIJTARAF water supply scheme, TW no I and II of under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000856/2022-2023 | 645/NMD-II | 23/03/2023 | 22/04/2023 | H.K DAS AND CO. | 21.63 | 0 | 0 | 10
2 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | FHTC AT NAJIRHAT PWSS |  |  | BILL/01100/2023-2024 | BP-687 | 19/10/2023 |  | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 12 | 0 | 0 | 0
3 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Execution of different works related to NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000321/2023-2024 | 1304/CD | 24/11/2023 | 23/01/2024 | UDAY CHAKI | 2.5 | 1.96 | 78.26 | 80
4 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Execution of different works related to NIJTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000587/2022-2023 | 1677/CD | 13/02/2023 | 13/07/2023 | M/S TORSHA CONSTRUCTION | 362.44 | 36.31 | 10.02 | 60
5 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Execution of different works related to A. NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000067/2023-2024 | 404/CD | 23/05/2023 | 22/06/2023 | M/S NARAYAN KR. GHOSH | 92.35 | 27.69 | 29.98 | 60
Total | [13 empty] | 490.93 | 65.96 | 13.44