## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for NIJTARAF water supply scheme, TW no I and II of under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000856/2022-2023 | 645/NMD-II | 23/03/2023 | 22/04/2023 | H.K DAS AND CO. | 21.63 | 0 | 0 | 10
2 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 102/CD | 26/04/2023 | 26/04/2023 | Resource Division | 79.93 | 0 | 0 | 0
3 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | FHTC AT NAJIRHAT PWSS |  |  | BILL/01100/2023-2024 | BP-687 | 19/10/2023 | 19/10/2023 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 12 | 0 | 0 | 0
4 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Execution of different works related to NIJTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000587/2022-2023 | 1677/CD | 13/02/2023 | 13/07/2023 | M/S TORSHA CONSTRUCTION | 362.44 | 0 | 0 | 60
5 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | EXECUTION OF DIFFERENT WORKS RELATED TO MADHYA HUDUMDANGA HEMKUMARI ZONE-II & NIJTARAF PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000537/2024-2025 | 2221/CD | 23/12/2024 | 21/02/2025 | TORSHA CONSTRUCTION | 69.04 | 0 | 0 | 0
6 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Execution of different works related to NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000321/2023-2024 | 1304/CD | 24/11/2023 | 23/01/2024 | UDAY CHAKI | 2.5 | 0 | 0 | 80
7 | COOCHBEHAR | Haldibari | Coochbehar Division | NIJTARAF PIPED WATER SUPPLY SCHEME at HALDIBARI. | SM/13120 | New | Execution of different works related to A. NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000067/2023-2024 | 404/CD | 23/05/2023 | 03/05/2025 | M/S NARAYAN KR. GHOSH | 92.35 | 0 | 0 | 60
Total | [13 empty] | 639.91 | 0 | 0