## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | Execution of different works related to MEGH NARAYANER KUTHI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 987/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000467/2022-2023 | 1518/CD | 19/01/2023 | 12/03/2025 | MS BIDYUT SARKAR | 380.6 | 293.74 | 77.18 | 90
2 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Megh Narayenerkuthi water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000700/2023-2024 | 2202/NMD-II | 28/07/2023 | 27/08/2023 | M/S UTPAL CHAKRABORTY & CO. | 21.19 | 21.08 | 99.47 | 100
3 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | Name of Work: Execution of different works related to MEGHNARAYANER KUTHI PWSS under JAL JEEVAN MISSION PART O | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000261/2023-2024 | 1029/CD | 22/09/2023 | 21/11/2023 | MS BIDYUT SARKAR | 74.93 | 74.88 | 99.93 | 100
4 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 197/CD | 27/04/2023 | 27/04/2023 | Resource Division | 18.33 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MEGH NARAYANER KUTHI PH NO-II |  |  | BILL/00567/2023-2024 | BP-2023-24-145 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MEGH NARAYANER KUTHI PH NO-I |  |  | BILL/00568/2023-2024 | BP-2023-24-144 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000068/2025-2026 | 753/CD | 17/05/2025 | 15/08/2025 | ANIMESH DHAR CHOUDHURY | 53.67 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000080/2025-2026 | 784/CD | 23/05/2025 | 21/08/2025 | GOUTAM KUMAR DAS | 92.33 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000329/2025-2026 | 704/CD | 17/05/2025 | 12/01/2026 | MS SSB CONSTRUCTION CO | 85.29 | 0 | 0 | 100
10 | COOCHBEHAR | Dinhata-II | Coochbehar Division | MEGH NARAYANER KUTHI PIPED WATER SUPPLY SCHEME. | SM/13136 | New | EXECUTION OF DIFFERENT WORKS (WITHIN MEGH NARAYANER KUTHI AREA) RELATED TO BANIADAHA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000693/2024-2025 | 228/CD | 12/02/2025 | 13/04/2025 | JANE MIA | 9.06 | 0 | 0 | 98
Total | [13 empty] | 737.41 | 389.7 | 52.85