## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jarabari Prathamkhanda water supply scheme, TW no I and II under NMD-II, PHE Dte.APD |  |  | ORD/000856/2023-2024 | 2440/NMD-II | 11/08/2023 | 10/09/2023 | CHOWDHURY AND BASU ENTERPRISE | 22.08 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | QUOTATION FOR NSC AT JARABARI PRATHAM KHANDA TW NO II |  |  | BILL/02462/2023-2024 | BP-2023-24-547 | 17/01/2024 |  | WBSEDCL | 10.72 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | QUOTATION FOR NSC AT JARABARI PRATHAM KHANDA TW NO I |  |  | BILL/02463/2023-2024 | BP-2023-24-546 | 17/01/2024 |  | WBSEDCL | 10.39 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to JARABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1209/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000578/2022-2023 | 1768/CD | 02/03/2023 | 08/10/2023 | MATARA CONSTRUCTION CO. | 609.12 | 133.45 | 21.91 | 60
5 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to DHT LAB area under JARABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000782/2023-2024 | 663/CD | 11/03/2024 | 10/05/2024 | BHAGWATI BHUJEL | 6.94 | 0 | 0 | 100
6 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to CHHOTO SAKDAL PWSS under JAL JEEVAN MISSION |  |  | ORD/000082/2024-2025 | 1320/CD | 19/07/2024 | 17/10/2024 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS. SOCY LTD. | 32.27 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to DINHATA (P) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000084/2024-2025 | 1189/CD | 18/06/2024 | 16/09/2024 | M/S J C ENTERPRISE | 80.91 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata - I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20561.72 | 133.45 | 0.65