## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to CHHOTO SAKDAL PWSS under JAL JEEVAN MISSION |  |  | ORD/000082/2024-2025 | 1320/CD | 19/07/2024 | 17/10/2024 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS. SOCY LTD. | 32.27 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to DHT LAB area under JARABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000782/2023-2024 | 663/CD | 11/03/2024 | 10/05/2024 | BHAGWATI BHUJEL | 6.94 | 6.91 | 99.63 | 100
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | QUOTATION FOR NSC AT JARABARI PRATHAM KHANDA TW NO I |  |  | BILL/02463/2023-2024 | BP-2023-24-546 | 17/01/2024 | 17/01/2024 | WBSEDCL | 10.39 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | QUOTATION FOR NSC AT JARABARI PRATHAM KHANDA TW NO II |  |  | BILL/02462/2023-2024 | BP-2023-24-547 | 17/01/2024 | 17/01/2024 | WBSEDCL | 10.72 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to JARABARI PRATHAM KHANDA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1209/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000578/2022-2023 | 1768/CD | 02/03/2023 | 02/06/2025 | MATARA CONSTRUCTION CO. | 609.12 | 458.6 | 75.29 | 76
6 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jarabari Prathamkhanda water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000856/2023-2024 | 2440/NMD-II | 11/08/2023 | 05/04/2025 | CHOWDHURY AND BASU ENTERPRISE | 22.08 | 0 | 0 | 80
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | EXECUTION OF DIFFERENT WORKS RELATED TO PAKHIHAGA & JARABARI PRATHAM KHANDA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000561/2024-2025 | 2246/CD | 23/12/2024 | 16/02/2026 | MATARA CONSTRUCTION CO. | 32.27 | 0 | 0 | 70
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | JARABARI PRATHAM KHANDA PIPED WATER SUPPLY SCHEME. | SM/13137 | New | Execution of different works related to DINHATA (P) & Adjacent Jarabari Pratham Khanda & Dakhshin Dighaltari PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000084/2024-2025 | 1189/CD | 18/06/2024 | 01/11/2025 | M/S J C ENTERPRISE | 80.91 | 1.8 | 2.23 | 85
Total | [13 empty] | 20593.99 | 467.31 | 2.27