## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 161/CD | 27/04/2023 | 27/04/2023 | Resource Division | 20.36 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of HARIBHANGA PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000502/2021-2022 | 1450/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 10.7 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | New service connection at Haribhanga Khattimari PWSS, P/H-II |  |  | BILL/02212/2023-2024 | BP-2023-24-489 | 21/12/2023 | 21/12/2023 | WBSEDCL | 10.41 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-II | Northern Mechanical Division II | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | New service connection at Haribhanga Khattimari PWSS, P/H-I. |  |  | BILL/02207/2023-2024 | BP-2023-24-486 | 21/12/2023 | 21/12/2023 | WBSEDCL | 5.72 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | Execution of different works related to HARIBHANGA KHATTIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000607/2022-2023 | 1612/CD | 03/02/2023 | 19/12/2025 | SASANKA ROY | 188.58 | 0 | 0 | 21
7 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | Execution of different works related to HARIBHANGA KHATTIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000392/2023-2024 | 1364/CD | 05/12/2023 | 01/08/2025 | SASANKA ROY | 29.34 | 0 | 0 | 50
8 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | EXECUTION OF DIFFERENT WORKS (within NAJIRGANJ, BHANGRI PRATHAM KHANDA, RUIER KHUTHI & HARIBHANGA KHATTIMARI area) RELATED TO Bhulki PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000655/2024-2025 | 84/CD | 17/01/2025 | 13/11/2025 | BIJOY ROY | 84.6 | 0 | 0 | 40
9 | COOCHBEHAR | Dinhata-II | Coochbehar Division | HARIBHANGA KHATTIMARI PIPED WATER SUPPLY SCHEME. | SM/13138 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
Total | [13 empty] | 472.95 | 0 | 0