## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA NACHINA PH NO-I |  |  | BILL/00564/2023-2024 | BP-2023-24-146 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | New service connection at bara nachina pwss, P/H-III |  |  | BILL/02056/2023-2024 | BP-2023-24-431 | 05/12/2023 | 05/12/2023 | WBSEDCL | 10.45 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA NACHINA PH NO-II |  |  | BILL/00565/2023-2024 | BP-2023-24-147 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Nachina water supply scheme, TW no I , II and III under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000659/2023-2024 | 1945/NMD-II | 24/07/2023 | 23/08/2023 | SARKAR ELECTRIC | 35.82 | 0 | 0 | 100
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000435/2023-2024 | 53/CD | 10/01/2024 | 10/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 48.55 | 0 | 0 | 100
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | HORDING/ SIGN BOARD FOR IEC CAMPAINING AT GP OFFICE / BLOCK OFFICE & DIFFERENT HEALTH CENTERS UNDER (Bara Nachina (P) PWSS) COOCH BEHAR DIVISION , PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000506/2024-2025 | 1791/CD | 30/09/2024 | 10/10/2024 | MAKHMALI ACTIVITY CLUSTER | 14.93 | 0 | 0 | 80
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 28/CD | 05/01/2024 | 05/01/2024 | Resource Division | 26.83 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | Execution of different works related to BARA NACHINA (P) PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1206/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000581/2022-2023 | 1771/CD | 02/03/2023 | 20/07/2025 | TAPAN CHANDA | 569.74 | 0 | 0 | 46
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | Execution of different works related 3rd Site of Baro Nachina PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000038/2023-2024 | 375/CD | 23/05/2023 | 11/07/2025 | TAPAN CHANDA | 75.19 | 0 | 0 | 83
10 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | Bara Nachina (P) PIPED WATER SUPPLY SCHEME. | SM/13145 | New | Hiring of inspection vehicle for office of the Assistant Engineer , Coochbehar Mechanical Sub- Division, I.C.W JJM works under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001997/2023-2024 | 1589/CMSD | 28/02/2024 | 28/03/2024 | DIPAK SARKAR | 0.35 | 0 | 0 | 100
Total | [13 empty] | 784.08 | 0 | 0