## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | Execution of different works related to CHAUDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000553/2022-2023 | 1610/CD | 03/02/2023 | 18/02/2025 | MAHENDRA CHHETRI | 283.09 | 142.87 | 50.47 | 80
2 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Chaudanga water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001028/2023-2024 | 2660/NMD-II | 04/09/2023 | 28/06/2025 | SAIKAT SINHA | 19.63 | 15.85 | 80.73 | 100
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 109/CD | 26/04/2023 | 26/04/2023 | Resource Division | 26.25 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | QUOTATION FOR NSC AT CHOWDANGA PH NO I |  |  | BILL/01021/2023-2024 | BP-2023-24-227 | 24/07/2023 | 24/07/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | QUOTATION FOR NSC AT CHOWDANGA PH NO II |  |  | BILL/01020/2023-2024 | BP-2023-24-229 | 24/07/2023 | 24/07/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | HIRING VEHICLE AT AE/SADAR FOR SEPT,2023 |  |  | BILL/01407/2023-2024 | BP-754 | 20/12/2023 | 20/12/2023 | PARAUDDIN MIAH | 0.18 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | Execution of different works at B/PINJARER JHAR PWSS |  |  | BILL/00727/2023-2024 | BP-258-P2 | 05/07/2023 | 05/07/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 2.15 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | FHTC AT KAUARDARA PWSS |  |  | BILL/00666/2023-2024 | BP-263 | 11/07/2023 | 11/07/2023 | SHIBA ENTERPRISE | 2.63 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (CHAUDANGA) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-D) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000508/2024-2025 | 1793/CD | 30/09/2024 | 10/10/2024 | MAKHMALI ACTIVITY CLUSTER | 30.35 | 0 | 0 | 90
10 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | Execution of different works related to CHAUDANGA PWSS under JAL JEEVAN MISSION | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000058/2024-2025 | 1337/CD | 24/07/2024 | 23/04/2025 | MAHENDRA CHHETRI | 61.34 | 0 | 0 | 30
11 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | CHAUDANGA PIPED WATER SUPPLY SCHEME. | SM/13146 | New | SUPPLY OF CI SPECIALS AT JAMALDAHAT PWSS |  |  | BILL/02060/2023-2024 | BP-1394 | 31/03/2024 | 31/03/2024 | SSPR VALVE MANUFACTURING PVT. LTD. | 9.66 | 0 | 0 | 0
Total | [13 empty] | 437.39 | 158.72 | 36.29