## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 247/CD | 27/04/2023 | 27/04/2023 | Resource Division | 30.45 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 90/CD | 11/01/2024 | 11/01/2024 | Resource Division | 16.55 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I,Sitai | Northern Mechanical Division II | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION CHARGES AT ANDARAN SINGIMARI TW-I |  |  | BILL/02872/2023-2024 | BP-2023-24-664 | 04/03/2024 | 04/03/2024 | WBSEDCL | 6.65 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I,Sitai | Northern Mechanical Division II | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT ANDARAN SINGIMARI TW II. |  |  | BILL/02871/2023-2024 | BP-2023-24-663 | 04/03/2024 | 04/03/2024 | WBSEDCL | 6.23 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | Execution of different works related to ANANDARAN SINGIMARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1239/1-5/NBC-1; Dt.: 02-02-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000536/2022-2023 | 1775/CD | 02/03/2023 | 02/04/2025 | GEETA CONSTRUCTION | 552.31 | 373.36 | 67.6 | 86
6 | COOCHBEHAR | Dinhata-I,Sitai | Northern Mechanical Division II | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Andaran Shingimari water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000866/2023-2024 | 2449/NMD-II | 11/08/2023 | 13/03/2025 | M/S B ENTERPRISE | 22.11 | 13.54 | 61.24 | 80
7 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN ANANDARAN SINGIMARI AREA ) BRAHMOTTAR CHATRA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000578/2024-2025 | 2262/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 33.98 | 0 | 0 | 100
9 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | EXECUTION OF DIFFERENT WORKS RELATED TO ANANDARAN SINGIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000580/2024-2025 | 2286/CD | 23/12/2024 | 25/06/2025 | GOUTAM KUMAR DAS | 36.39 | 0 | 0 | 100
10 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000051/2025-2026 | 722/CD | 17/05/2025 | 15/08/2025 | GOUTAM KUMAR DAS | 32.95 | 0 | 0 | 100
11 | COOCHBEHAR | Dinhata-I,Sitai | Coochbehar Division | ANANDARAN SINGIMARI PIPED WATER SUPPLY SCHEME. | SM/13147 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000330/2025-2026 | 759/CD | 17/05/2025 | 13/11/2025 | M/S. MANDAL CONSTRUCTION | 32.05 | 0 | 0 | 50
Total | [13 empty] | 20558.96 | 386.9 | 1.88