## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | FHTC AT HEMKUMARI PWSS |  |  | VCH/001038/2022-2023 | 429 | 30/11/2022 | 30/11/2022 | M/S. MANDAL CONSTRUCTION | 6.61 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | Providing FHTC & other allied works at HEMKUMARI ZONE II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000510/2022-2023 | 1583/CD | 01/02/2023 | 03/03/2023 | NARESH CH.MANDAL | 9.98 | 9.12 | 91.45 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Hemkumari water supply scheme, TW no. Iand II of Zone-II and TW no. Iand II of Zone-III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000750/2023-2024 | 2316/NMD-II | 01/08/2023 | 31/08/2023 | DEY ENTERPRISE (BALLY) | 41.65 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | Preparation of DPR for Augmentation of HEMKUMARI (Zone-II) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000169/2022-2023 | 628/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.02 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 191/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.33 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO MADHYA HUDUMDANGA HEMKUMARI ZONE-II & NIJTARAF PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000537/2024-2025 | 2221/CD | 23/12/2024 | 21/02/2025 | TORSHA CONSTRUCTION | 69.04 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE DINHATA MEKLIGANJ ADJACENT HEMKUMARI Z 2 road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, |  |  | BILL/00370/2024-2025 | BP-308 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 2.99 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDESHIBPUR BAWRAH ADJACENT HEMKUMARI road VR ( IN stretches FROM 0.00 KM TO 8.00 KM UNDER MATHABHANGA SUB DIVISION UNDER PWD Cooch Behar division DURING YEAR 2024-2025 |  |  | BILL/00371/2024-2025 | BP-309 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 10.62 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDEGOBRACHOWRA CHOWPATHI TO AMBARI BAZAR ALLAR BAZAR BHAGNIR PART ADJACENT HEMKUMARI Z 2road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, |  |  | BILL/00369/2024-2025 | BP-307 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 10.62 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | Execution of different works related to HEMKUMARI ZONE 2 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 31/1-5/NBC-1; Dt.: 13-04-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000002/2023-2024 | 51/CD | 17/04/2023 | 14/09/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 317.41 | 151.82 | 47.83 | 30
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO HEMKUMARI ZONE-II HEMKUMARI ZONE-III & DAKSHIN SAMILABAS PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000532/2024-2025 | 2216/CD | 23/12/2024 | 15/04/2026 | M/S N S CONSTRUCTION | 39.17 | 0 | 0 | 50
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASE HEMKUMARI ZONE-II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION . | SM/13148 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000277/2025-2026 | 737/CD | 17/05/2025 | 12/02/2026 | SANKAR CHAKRABORTY | 39.09 | 0 | 0 | 95
Total | [13 empty] | 20355.81 | 160.94 | 0.79