## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Execution of different works related to JIRANPUR PART B PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1119/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000576/2022-2023 | 1856/CD | 14/03/2023 | 02/04/2025 | MALAY KR.DEB | 288.97 | 77.42 | 26.79 | 39
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Name of Work: Execution of different works related to (Within area of DEWANHAT) JIRANPUR ZONE-I (B) PWSS under JAL JEEVAN MISSION PART D | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000254/2023-2024 | 1021/CD | 22/09/2023 | 27/01/2025 | SIDHARTHA ROY | 47.65 | 0 | 0 | 100
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 110/CD | 26/04/2023 | 26/04/2023 | Resource Division | 14.3 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO CHANDAMARI JIRANPUR ZONE-I (B) & CHILKIRHAT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000536/2024-2025 | 2220/CD | 23/12/2024 | 21/02/2025 | GOUTAM KUMAR DAS | 95.69 | 0 | 0 | 30
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO PWSS JIRANPUR ZONE-I (B) & KARIMALA KHAGRABARI (CT) UNDER JAL JEEVAN MISSION. |  |  | ORD/000564/2024-2025 | 2249/CD | 23/12/2024 | 21/02/2025 | ASHIM KUMAR CHAKRABORTY | 18.3 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRANPUR PWSS |  |  | BILL/02010/2023-2024 | BP-1398 | 31/03/2024 | 31/03/2024 | BIJOY ROY | 2 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector forGround Water Based Piped Water Supply Scheme AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B),P/H No- I and II ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION under Jal Jeevan Mission NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000057/2025-2026 | 1151/NMD-II | 16/05/2025 | 15/06/2025 | CHOWDHURY AND BASU ENTERPRISE | 21.57 | 0 | 0 | 0
Total | [13 empty] | 598.31 | 77.42 | 12.94