## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 110/CD | 26/04/2023 |  | Resource Division | 14.3 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Jiranpur Water Supply Scheme Zone - I (B) TW No.-I AND II under NMD-II,PHE.Dte,Apd |  |  | ORD/000897/2023-2024 | 2483/NMD-II | 11/08/2023 | 10/09/2023 | ANUP BASU | 20.77 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRANPUR PWSS |  |  | BILL/02010/2023-2024 | BP-1398 | 31/03/2024 |  | BIJOY ROY | 2 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORK AT ABUAR PATHAR PWSS |  |  | BILL/02068/2023-2024 | BP-1115 | 02/03/2024 |  | S & P ENTERPRISE | 152.3 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 |  | MALAY KR.DEB | 109.82 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER JIRANPUR ZONE-I (B) ACCOMODATE FHTC IN HALDIBARI BLOCK WITHIN COOCH BEHAR DISTRICT UNDE COOCH BEHAR DIVISION | SM/13149 | Augmentation | Execution of different works related to JIRANPUR PART B PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1119/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000576/2022-2023 | 1856/CD | 14/03/2023 | 11/08/2023 | MALAY KR.DEB | 288.97 | 36.35 | 12.58 | 39
Total | [13 empty] | 588.16 | 36.35 | 6.18