## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | Supply of CC Camera and its different allied accessories including fitting fixing and installation at the office of the Executive Engineer, Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000275/2022-2023 | 876/CD. | 21/09/2022 | 28/09/2022 | CYBERNET | 0.98 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 193/CD | 27/04/2023 |  | Resource Division | 19.5 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Hemkumari water supply scheme, TW no. Iand II of Zone-II and TW no. Iand II of Zone-III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000750/2023-2024 | 2316/NMD-II | 01/08/2023 | 31/08/2023 | DEY ENTERPRISE (BALLY) | 41.65 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT HEMKUMARI PWSS TW III |  |  | BILL/02726/2023-2024 | BP-2023-24-595 | 15/02/2024 |  | WBSEDCL | 3.73 | 0 | 0 | null
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | Execution of different works with in G CHOWRANGEE related to HEMKUMARI PWSS ZONE-III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000604/2023-2024 | 649/CD | 11/03/2024 | 10/05/2024 | TAPAN CHANDA | 97.79 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | Execution of different works related to HEMKUMARI ZONE 3 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1106/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000671/2022-2023 | 1884/CD | 14/03/2023 | 11/08/2023 | UNIBRO INFRASERV PRIVATE LIMITED | 345.67 | 0 | 0 | 30
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF HEMKUMARI PWSS ZONE-III | SM/13150 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20298.61 | 0 | 0