## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Providing 150 nos F.H.T.C. for JIRANPUR (Part-C) W.S.S. under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000102/2022-2023 | 215/SD | 27/06/2022 | 27/07/2022 | KARTICK CH SEAL | 4.82 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 1347/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Providing FHTC & other allied works at JIRANPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000232/2022-2023 | 718/CD | 27/08/2022 | 11/10/2022 | NANDALAL SARKAR | 19.98 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Execution of different works related to JIRANPUR PART A PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1120/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000609/2022-2023 | 1847/CD | 10/03/2023 | 07/08/2023 | BIJOY ROY | 173.69 | 0 | 0 | 90
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Preparation of DPR for Augmentation of Jiranpur Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000298/2021-2022 | 1013/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.1 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Preparation of DPR for Augmentation of JIRANPUR Piped Water Supply Scheme under COOCH BEHAR SADAR Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000166/2022-2023 | 625/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.62 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Execution of different works related to JIRANPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000164/2023-2024 | 941/CD | 04/09/2023 | 03/12/2023 | BIJOY ROY | 96.23 | 0 | 0 | 73
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Execution of different works related to JIRANPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000553/2023-2024 | 602/CD | 11/03/2024 | 10/05/2024 | BIJOY ROY | 55.87 | 0 | 0 | 30
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | NEW SERVICE CONNECTION CHARGES AT JIRANPUR PWSS ZONE-II, PH-II |  |  | BILL/02745/2023-2024 | BP-2023-24-617 | 16/02/2024 | 16/02/2024 | WBSEDCL | 8.46 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | NEW SERVICE CONNECTION CHARGES FOR JIRANPUR PWSS, ZONE-II, PH- I |  |  | BILL/02746/2023-2024 | BP-2023-24-616 | 16/02/2024 | 16/02/2024 | WBSEDCL | 7.63 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Augumentation of JIRANPUR water supply scheme, TW no I of Zone-I (A) under JJM under NMD-II, PHE Dte. APD. |  |  | ORD/000802/2023-2024 | 2384/NMD-II | 09/08/2023 | 08/09/2023 | GOENKA ENTERPRISE | 10.85 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF JIRANPUR ZONE-I (A) PWSS. | SM/13151 | Augmentation | Execution of different works (WITHIN HARINCHAOWRA & BOGDABARI KESAIBARI AREA) related to JIRANPUR PWSS under JAL JEEVAN MISSION P B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000679/2024-2025 | 1184/CD | 18/06/2024 | 13/06/2025 | MALAY KR.DEB | 66.85 | 0 | 0 | 35
Total | [13 empty] | 567.4 | 0 | 0