## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1350/CD | 19/12/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Preparation of DPR for Augmentation of KHATTIMARI (Zone-II) Piped Water Supply Scheme under COOCH BEHAR SADAR Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000167/2022-2023 | 626/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.83 | 2.83 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 163/CD | 27/04/2023 |  | Resource Division | 13.81 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Khattimari (Dinhata -II) water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte. APD |  |  | ORD/000826/2023-2024 | 2395/NMD-II | 09/08/2023 | 08/09/2023 | M/S ABHISEK ENGINEERING CONCERN | 20.81 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | QUOTATION FOR NSC AT KHATTIMARI ZONE-II TW NO-I |  |  | BILL/01803/2023-2024 | BP-2023-24-334 | 27/09/2023 |  | WBSEDCL | 8.08 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Execution of different works related to AUG. of KHATTIMARI ZONE-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000523/2022-2023 | 1678/CD | 13/02/2023 | 13/07/2023 | AMBITIOUS ENTERPRISE | 345.5 | 90.01 | 26.05 | 6
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | FUEL BILL |  |  | BILL/02073/2023-2024 | BP-1413 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 1.52 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | HIRING VEHICLE FOR AE/TFG |  |  | BILL/00481/2024-2025 | BP-208 | 31/07/2024 |  | MATRI ENTERPRISEES | 0.72 | 0 | 0 | 0
Total | [13 empty] | 20244.15 | 92.85 | 0.46