## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1350/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Preparation of DPR for Augmentation of KHATTIMARI (Zone-II) Piped Water Supply Scheme under COOCH BEHAR SADAR Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000167/2022-2023 | 626/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.83 | 2.83 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 163/CD | 27/04/2023 | 27/04/2023 | Resource Division | 13.81 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | QUOTATION FOR NSC AT KHATTIMARI ZONE-II TW NO-I |  |  | BILL/01803/2023-2024 | BP-2023-24-334 | 27/09/2023 | 27/09/2023 | WBSEDCL | 8.08 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Execution of different works related to AUG. of KHATTIMARI ZONE-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000523/2022-2023 | 1678/CD | 13/02/2023 | 13/07/2023 | AMBITIOUS ENTERPRISE | 345.5 | 99.02 | 28.66 | 6
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | HIRING VEHICLE FOR AE/TFG |  |  | BILL/00481/2024-2025 | BP-208 | 31/07/2024 | 31/07/2024 | MATRI ENTERPRISEES | 0.72 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | FUEL BILL |  |  | BILL/02073/2023-2024 | BP-1413 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.52 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Khattimari (Dinhata -II) water supply scheme, TW no I and II of Zone-II under Northern Mechanical Division-II, PHE Dte. APD |  |  | ORD/000826/2023-2024 | 2395/NMD-II | 09/08/2023 | 08/09/2023 | M/S ABHISEK ENGINEERING CONCERN | 20.81 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000017/2025-2026 | 702/CD | 17/05/2025 | 13/11/2025 | UMEX POLYMERS PVT LTD | 37.04 | 0 | 0 | 60
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Khattimari Zone-II PWSS (Dinhata-II) | SM/13153 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000093/2025-2026 | 746/CD | 17/05/2025 | 15/08/2025 | SANJAY MANDAL | 20.3 | 0 | 0 | 0
Total | [13 empty] | 20301.49 | 101.85 | 0.5