## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 1349/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Preparation of DPR for Augmentation of Kuchlibari Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000293/2021-2022 | 1008/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.96 | 2.75 | 92.85 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | FHTC AT KUCHLIBARI Z-I PWSS |  |  | BILL/01085/2023-2024 | BP-595 | 13/10/2023 | 13/10/2023 | MANABENDRA DE | 15 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | QUOTATION FOR BURNT METER AT KUCHLIBARI PWSS |  |  | BILL/01003/2023-2024 |  | 07/07/2023 | 07/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for KUCHLIBARI TW NO.II OF ZONE-I,T/W NO.IV Water Supply Scheme under NMDII, PHE. Dte, APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000705/2023-2024 | 2061/NMD-II | 26/07/2023 | 25/08/2023 | RMD TRADING | 21.17 | 0 | 0 | 50
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Kuchlibari Zone-I, KUCHLIBARI ZONE-II AND ANDARAN KUCHLIBARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000527/2024-2025 | 2290/CD | 23/12/2024 | 21/02/2025 | M/S BADAL CH SAHA | 94.71 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Execution of different works related to KUCHLIBARI Z 1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1294/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000605/2022-2023 | 1901/CD | 17/03/2023 | 01/02/2024 | M/S PALIT ENTERPRISE | 145.76 | 75.03 | 51.47 | 80
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | ELECTRIC QUOTATION BILL FOR BURNT METER AT KUCHLIBARI PWSS TW NO. V. |  |  | BILL/02239/2023-2024 | BP-2023-24-487 | 21/12/2023 | 21/12/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000271/2025-2026 | 743/CD | 17/05/2025 | 15/08/2025 | M/S BADAL CH SAHA | 96.84 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Execution of different works related (within area of SOULMARI) to Kuchlibari Zone-I PWSS under JAL JEEVAN MISSION MKG | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000522/2023-2024 | 320/cd | 09/02/2024 | 04/06/2025 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 2.73 | 2.07 | 75.72 | 30
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | Execution of different works related to KUCHLIBARI Z-I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000516/2023-2024 | 314/CD | 09/02/2024 | 03/10/2025 | M/S PALIT ENTERPRISE | 28.65 | 26.53 | 92.58 | 30
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Kuchlibari Zone-I PWSS ((Mekhliganj Block) | SM/13154 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000077/2025-2026 | 650/CD | 05/05/2025 | 29/07/2026 | SUPER -TECH ENGINEERS'CO-OPERATIVE SOCIETY LIMITED | 69.03 | 0 | 0 | 60
Total | [13 empty] | 20327.93 | 106.37 | 0.52