## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Execution of different works related to PUTIABARO MASIA ZONE 1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1011/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000495/2022-2023 | 1560/CD | 24/01/2023 | 23/06/2023 | SHREE RANI SATI ENTERPRISE | 350.47 | 123.52 | 35.24 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Providing FHTC & other allied works at PUTIA BAROMASIA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000511/2022-2023 | 1584/CD | 01/02/2023 | 03/03/2023 | SUBODH ROY & SONS | 9.97 | 9.96 | 99.96 | 100
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 233/CD | 27/04/2023 | 27/04/2023 | Resource Division | 25.92 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Providing FHTC & other allied works in the command area of KISMAT DASGRAM PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000509/2023-2024 | 306/CD | 09/02/2024 | 09/04/2024 | SHREE RANI SATI ENTERPRISE | 34.93 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Renovation of Laying Distribution System of pipe line Harinkuchi Swapna-Baromasia, Khanka & Dogarpar under PUTIA BAROMASIA PWSS under Cooch Behar Divn., PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000129/2020-2021 | 1386/CD | 07/01/2021 | 02/04/2022 | NABIN DEBNATH | 13.94 | 0 | 0 | 1
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Putia Baramasia water supply scheme, TW no III of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar |  |  | ORD/000853/2023-2024 | 2439/NMD-II | 11/08/2023 | 10/09/2023 | MASSK ENGINEERING WORKS | 11.07 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Execution of different works related to PUTIA BAROMASIA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000370/2023-2024 | 1389/CD | 05/12/2023 | 05/08/2025 | SIBAPADA SINGHA ROY | 32.43 | 6.89 | 21.26 | 60
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000076/2025-2026 | 649/CD | 05/05/2025 | 03/08/2025 | GOUTAM KUMAR DAS | 67.3 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000271/2025-2026 | 743/CD | 17/05/2025 | 15/08/2025 | M/S BADAL CH SAHA | 96.84 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-I PWSS (Sitalkuchi Block) | SM/13155 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 75/CD | 15/01/2025 | 15/01/2025 | Resource Division | 61.6 | 0 | 0 | 0
Total | [13 empty] | 20493.76 | 140.38 | 0.68