## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 232/CD | 27/04/2023 |  | Resource Division | 59.17 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PUTIA BARAMASIA (AUG) Z-II,PH NO-I |  |  | BILL/00148/2023-2024 | BP-2023-24-106 | 18/05/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PUTIA BARAMASIA (AUG) Z-II,PH NO-II |  |  | BILL/00149/2023-2024 | BP-2023-24-107 | 18/05/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Puttia Baramasia water supply scheme, TW no I,II,III & IV of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000851/2023-2024 | 2428/NMD-II | 10/08/2023 | 09/09/2023 | AHALYA ENGINEERING WORKS | 44.31 | 18.29 | 41.28 | 30
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | Execution of different works related to PUTIABARO MASIA Z- II PWSS under JAL JEEVAN MISSION |  |  | ORD/000496/2023-2024 | 298/CD | 09/02/2024 | 09/04/2024 | SHREE RANI SATI ENTERPRISE | 47.38 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | Execution of different works related to PUTIABARO MASIA ZII PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1212/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000542/2022-2023 | 1781/CD | 02/03/2023 | 30/07/2023 | Z STAR COMMOTRADE PVT LTD | 561.21 | 206.42 | 36.78 | 100
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING JIKABARI GHAT TO KAWARGHAT ROAD ADJACENT HEMKUMARI ADJACENT PUTIA BARA MASIA road VR ( IN stretches FROM 0.00 KM TO 3.50 KM UNDER MATHABHANGA SUB DIVISION UNDER PWD Cooch Behar division DURING YEAR 2024-2025 |  |  | BILL/00372/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 7.12 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSID 5 NO BAZAR BHOWMIK PARA ADJACENT PUTIA BARA MASIA road VR ( IN stretches FROM 0.00 KM TO 4.00 KM UNDER MATHABHANGA SUB DIVISION UNDER PWD Cooch Behar division DURING YEAR 2024-2025 |  |  | BILL/00373/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 7.02 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Putia Bara Masia Zone-II (Sitalkuchi Block) | SM/13156 | Augmentation | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDUDUYAR PAR TO FULBARI HOSPITAL MORE ROAD ADJACENT PUTIA BARA MASIA road VR ( IN stretches FROM 0.00 KM TO 8.00 KM UNDER MATHABHANGA SUB DIVISION UNDER PWD Cooch Behar division DURING YEAR 2024-2025 |  |  | BILL/00374/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 5.19 | 0 | 0 | 0
Total | [13 empty] | 20522.81 | 224.71 | 1.09