## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Providing functional house hold tap connection within command area of Uchalpukuri Zone-I Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000154/2022-2023 | 210/MTB | 26/07/2022 | 10/08/2022 | BISWAJIT GUHA | 4.79 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 1344/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Preparation of DPR for Augmentation of UCHALPUKRI (Zone-II) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000163/2022-2023 | 622/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.61 | 3.61 | 100 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Execution of different works related to UCHALPUKURI ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1121/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000572/2022-2023 | 1690/CD | 13/02/2023 | 13/07/2023 | PALLAB BHAWAL | 494 | 406.23 | 82.23 | 45
5 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT UCHAL PUKHRI ZONE-II TW III. |  |  | BILL/00514/2024-2025 | BP-123/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.54 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Uchalpukhari water supply scheme, TW no. III of Zone-I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000828/2023-2024 | 2396/NMD-II | 09/08/2023 | 02/09/2025 | SARKAR ELECTRIC | 20.8 | 0 | 0 | 80
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Shifting pipeline due to widening & strengthening of Jamaldah Ranirhat via Uchalpukuri Z-II road from 0.00 km to 12.70 km by COB Highway Divn.-III under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000120/2021-2022 | 312/CD | 13/08/2021 | 26/08/2025 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 45.47 | 17.17 | 37.76 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | Hiring of Diesel Vehicle for Executive Engineer for inspection of site checking of FHTC and LDS, searching of land for different PWSS under Cooch Behar Division, PHE Dte. (From 01-07-24 to 30-06-2025). |  |  | ORD/000461/2024-2025 | 1233/CD | 29/06/2024 | 29/06/2025 | RAJESH GUPTA | 2.15 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO UCHALPUKURI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000553/2024-2025 | 2238/CD | 23/12/2024 | 10/10/2025 | MAHARAJA CONSTRUCTION CO. | 94.56 | 0 | 0 | 30
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based UCHALPUKURI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in Mekhliganj Block within Cooch Behar District under Cooch Behar Division, P.H.E. Dte. | SM/13157 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000280/2025-2026 | 787/CD | 23/05/2025 | 21/08/2025 | CONSTRUCTION DEVELOPMENT PROJECT | 79.37 | 0 | 0 | 0
Total | [13 empty] | 20710.01 | 427.01 | 2.06