## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 222/CD | 27/04/2023 | 27/04/2023 | Resource Division | 7.15 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | Execution of different works related to TATERKUTHI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1292/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000613/2022-2023 | 1908/CD | 17/03/2023 | 05/04/2025 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 205.66 | 149.08 | 72.49 | 70
3 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | New service connection at Taterkuthi PWSS, P/H-II |  |  | BILL/02721/2023-2024 | BP-2023-24-597 | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.43 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | New service connection at Taterkuthi PWSS, P/H-I |  |  | BILL/02720/2023-2024 | BP-2023-24-596 | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
5 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Taterkuthi water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000997/2023-2024 | 2634/NMD-II | 28/08/2023 | 27/09/2023 | M/S UTPAL CHAKRABORTY & CO. | 19.64 | 0 | 0 | 60
6 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within TATERKUTHI & JHINGAPUNI area) MAHISKUCHI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000594/2024-2025 | 2278/CD | 23/12/2024 | 21/02/2025 | UTPAL CHAKRABORTY | 66.76 | 0 | 0 | 70
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TATERKUTHI KHAGRIBARI GORBHANGA & FALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000557/2024-2025 | 2242/CD | 23/12/2024 | 21/02/2025 | HARIDAS GHOSH | 65.94 | 1.05 | 1.59 | 60
8 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | TATERKUTHI PIPED WATER SUPPLY SCHEME. | SM/13158 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000275/2025-2026 | 739/CD | 17/05/2025 | 15/08/2025 | DAS ENTERPRISE | 37.76 | 0 | 0 | 0
Total | [13 empty] | 412.04 | 150.13 | 36.44