## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 162/CD | 27/04/2023 |  | Resource Division | 17.89 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Soulmari (Dinhata-II) water supply scheme, TW no. I and II of Zone-Iand II under Northern Mechanical Division-II, PHE Dte.Alipurduar. |  |  | ORD/000827/2023-2024 | 2397/NMD-II | 09/08/2023 | 08/09/2023 | DAS ENTERPRISE | 41.51 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Execution of different works related to SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000068/2023-2024 | 405/CD | 23/05/2023 | 22/06/2023 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 27.32 | 26.78 | 98.03 | 100
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Execution of different works related to GOSANIMARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000529/2023-2024 | 324/CD | 09/02/2024 | 09/04/2024 | MS BIDYUT SARKAR | 61.55 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Execution of different works related to SOULMARI Z- II PWSS under JAL JEEVAN MISSION DHT | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000503/2023-2024 | 299/CD | 09/02/2024 | 09/04/2024 | SWAPAN KUMAR ROY | 95.77 | 0 | 0 | 85
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Execution of different works related to SOULMARI Z 2 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1009/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000497/2022-2023 | 1562/CD | 24/01/2023 | 23/06/2023 | SWAPAN KUMAR ROY | 365.46 | 0 | 0 | 78
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Execution of different works related to AUG. SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000055/2024-2025 | 1269/CD | 02/07/2024 | 30/09/2024 | M/S A. B. ENTERPRISE | 39.89 | 0 | 0 | 30
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Charges for new service connection at Soulmari (Zone-II) PWSS, P/H-I in the dist of Coochbehar |  |  | BILL/00838/2024-2025 | BP-257/24-25 | 08/08/2024 |  | WBSEDCL | 3.99 | 0 | 0 | null
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Charges for new service connection at Soulmari (Zone-II) PWSS, P/H-I in the dist of Coochbehar |  |  | BILL/00838/2024-2025 | BP-257/24-25 | 08/08/2024 |  | WBSEDCL | 3.99 | 0 | 0 | null
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Charges for new service connection at Soulmari (Zone-II) PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/00839/2024-2025 | BP-256/24-25 | 06/08/2024 |  | WBSEDCL | 5.39 | 0 | 0 | null
11 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Soulmari Zone-II Piped Water Supply Scheme(Dinhata-II) | SM/13159 | Augmentation | Charges for new service connection at Soulmari (Zone-II) PWSS, P/H-II in the dist of Coochbehar. |  |  | BILL/00839/2024-2025 | BP-256/24-25 | 06/08/2024 |  | WBSEDCL | 5.39 | 0 | 0 | null
Total | [13 empty] | 668.14 | 26.78 | 4.01