## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | Preparation of DPR for Augmentation of Satkura Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000301/2021-2022 | 1016/CD | 10/01/2022 | 30/01/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 3.17 | 3.1 | 97.64 | 1
2 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | FHTC AT SATKURA PWSS (P-B) |  |  | VCH/001027/2022-2023 | 417 | 14/11/2022 | 14/11/2022 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.82 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | FHTC AND OTHER ALL9IED WORKS AT SATKURA PWSS (P-A) |  |  | VCH/001063/2022-2023 | 456 | 30/11/2022 | 30/11/2022 | SOMNATH MUKHERJEE | 4.82 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | FHTC AT SATKURA PWSS (P-C) |  |  | VCH/001039/2022-2023 | 430 | 30/11/2022 | 30/11/2022 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.82 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Satkura water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000657/2023-2024 | 1960/NMD-II | 24/07/2023 | 23/08/2023 | RIPON DAS | 10.81 | 2.66 | 24.64 | 80
6 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | Execution of different works related to CHHOTO SAKDAL PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000346/2023-2024 | 1330/CD | 24/11/2023 | 18/11/2024 | SHIBA ENTERPRISE | 66.37 | 23.33 | 35.16 | 50
7 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | Execution of different works related to SATKURA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1015/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000491/2022-2023 | 1556/CD | 24/01/2023 | 09/12/2025 | SHIBA ENTERPRISE | 293.48 | 253.33 | 86.32 | 100
8 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 169/CD | 27/04/2023 | 27/04/2023 | Resource Division | 12.31 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT SATKURA (REJU) PH NO-III |  |  | BILL/00570/2023-2024 | BP-2023-24-143 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SATKURA & PETLA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000560/2024-2025 | 2245/CD | 23/12/2024 | 21/06/2025 | RAHAMAN ENTERPRISE | 19.43 | 0 | 0 | 90
11 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED (WITHIN REJ BARA ATIABARI PRATHAM KHANDA and REJ SATKURA AREA) TO Nigamnagar PWSS UNDER JAL JEEVAN MISSION. Part-A | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000015/2025-2026 | 644/CD | 05/05/2025 | 03/08/2025 | TAPAN CHANDA | 91.01 | 0 | 0 | 100
13 | COOCHBEHAR |  | Coochbehar Division | REJUVENATION OF SATKURA PIPED WATER SUPPLY SCHEME | SM/13160 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000292/2025-2026 | 1422/CD | 11/08/2025 | 09/12/2025 | M/S SURAJIT MAJUMDER | 29.52 | 0 | 0 | 50
Total | [13 empty] | 651.42 | 282.43 | 43.36