## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 188/CD | 27/04/2023 | 27/04/2023 | Resource Division | 19.93 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | ELECTRIC QUOTATION BILL FOR NSC AT BARA GOPALPUR TW I |  |  | BILL/02047/2023-2024 | BP-2023-24-424 | 05/12/2023 | 05/12/2023 | WBSEDCL | 4.31 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Gopalpur water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001128/2023-2024 | 2871/NMD-II | 17/10/2023 | 16/11/2023 | RMD TRADING | 22.08 | 0 | 0 | 70
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | Execution of different works related to BARO GOPALPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000361/2023-2024 | 1396/CD | 05/12/2023 | 03/02/2024 | SUBHAS CHANDRA ROY | 52.75 | 0 | 0 | 70
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | EXECUTION OF DIFFERENT WORKS AT KHAGRABARI PWSS |  |  | BILL/01320/2023-2024 | BP-816 | 22/12/2023 | 22/12/2023 | BIJOY ROY | 7.78 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | PROVIDING INTERNET CONNECTION |  |  | BILL/00598/2024-2025 | BP-233 | 01/08/2024 | 01/08/2024 | BIJOY ROY | 0.11 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | ADDITIONAL QUOTATION AMOUNT PAYABLE FOR CHANGE OF ROUT LENGTH AT BARAGOPALPUR TW I |  |  | BILL/01401/2024-2025 | BP-399/24-25 | 29/10/2024 | 29/10/2024 | WBSEDCL | 4.06 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | EXECUTION OF DIFFERENT WORK AT JAIGIRI CHILAKHANA PWSS |  |  | BILL/02053/2023-2024 | BP-1400 | 31/03/2024 | 31/03/2024 | GHOSH AND SAHA CONSTRUCTION | 4.98 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | FHTC AT KHAGRABARI PWSS |  |  | BILL/01392/2023-2024 | BP-830-P2 | 30/12/2023 | 30/12/2023 | AASHIRBAD ENTERPRISE | 0.5 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BARAGOPALPUR TW II. |  |  | BILL/00518/2024-2025 | BP-121/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 4.01 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | Execution of different works related to BARA GOPALPUR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1109/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000586/2022-2023 | 1671/CD | 13/02/2023 | 04/03/2025 | SUBHAS CHANDRA ROY | 324.18 | 0 | 0 | 10
12 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | BARA GOPALPUR PIPED WATER SUPPLY SCHEME. | SM/13161 | New | EXECUTION OF DIFFERENT WORKS (within PANIGRAM & BARA GOPALPUR area) RELATED TO KHARIJA KHAWARDARA PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000659/2024-2025 | 88/CD | 17/01/2025 | 18/03/2025 | GOUTAM KUMAR DAS | 57.5 | 0 | 0 | 0
Total | [13 empty] | 502.21 | 0 | 0