## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA NALANGIMARI TW NO-II |  |  | BILL/00163/2023-2024 | BP-2023-24-122 | 18/05/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA NALANGIMARI TW NO-I |  |  | BILL/00162/2023-2024 | BP-2023-24-123 | 18/05/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Nalangibari water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000748/2023-2024 | 2281/NMD-II | 31/07/2023 | 30/08/2023 | SOUMEN ELECTRIC | 21.63 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Execution of different works related to BARA NALANGIBARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1004/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000502/2022-2023 | 1567/CD | 24/01/2023 | 23/06/2023 | S N POLYMERS PVT LTD | 425.82 | 204.51 | 48.03 | 29
5 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | EXECUTION OF DIFFERENT WORKS AT UCHALPUKHARI PWSS |  |  | BILL/01104/2023-2024 | BP-625 | 13/10/2023 |  | PALLAB BHAWAL | 5.89 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Execution of different works related to BARO NALANGIBARI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000018/2024-2025 | 1126/CD | 14/06/2024 | 13/08/2024 | GOUTAM KUMAR DAS | 88.54 | 0 | 0 | 30
8 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 1536/CD | 16/08/2024 |  | Resource Division | 4.39 | 0 | 0 | 0
Total | [13 empty] | 20337.66 | 204.51 | 1.01