## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 98/CD | 26/04/2023 | 26/04/2023 | Resource Division | 2.35 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA NALANGIMARI TW NO-II |  |  | BILL/00163/2023-2024 | BP-2023-24-122 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | EXECUTION OF DIFFERENT WORKS AT UCHALPUKHARI PWSS |  |  | BILL/01104/2023-2024 | BP-625 | 13/10/2023 | 13/10/2023 | PALLAB BHAWAL | 5.89 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA NALANGIMARI TW NO-I |  |  | BILL/00162/2023-2024 | BP-2023-24-123 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Execution of different works related to BARA NALANGIBARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1004/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000502/2022-2023 | 1567/CD | 24/01/2023 | 23/06/2023 | S N POLYMERS PVT LTD | 425.82 | 274.76 | 64.53 | 29
6 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Execution of different works related to BARO NALANGIBARI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000018/2024-2025 | 1126/CD | 14/06/2024 | 13/08/2024 | GOUTAM KUMAR DAS | 88.54 | 51.32 | 57.96 | 30
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 1536/CD | 16/08/2024 | 16/08/2024 | Resource Division | 4.39 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000002/2025-2026 | 709/CD | 17/05/2025 | 13/12/2025 | M/S MAA MANASA CONSTRUCTION CO. | 34.86 | 0 | 0 | 50
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
12 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BARA NALANGIBARI PIPED WATER SUPPLY SCHEME. | SM/13162 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Nalangibari water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000748/2023-2024 | 2281/NMD-II | 31/07/2023 | 10/07/2025 | SOUMEN ELECTRIC | 21.63 | 0 | 0 | 100
Total | [13 empty] | 20511.81 | 326.08 | 1.59