## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | Providing FHTC & Laying P/Line at BARO PINJARERJHAR PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000019/2022-2023 | 35/CD | 07/04/2022 | 22/05/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 26.88 | 0 | 0 | 1
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA PINJARIR JHAR PH NO-II |  |  | BILL/00147/2023-2024 | BP-2023-24-104 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BARA PINJARIR JHAR Z-II,PH NO-I |  |  | BILL/00146/2023-2024 | BP-2023-24-105 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | Execution of different works related to BARA PINJARIRJHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER | ORD/000590/2022-2023 | 1674/CD | 13/02/2023 | 14/05/2023 | M/S DHAR ENTERPRISE | 474.75 | 0 | 0 | 41
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BARA PINJARERJHAR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000598/2024-2025 | 2299/CD | 23/12/2024 | 21/02/2025 | TORSHA CONSTRUCTION | 49.93 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for BARA PINJARER JHAR PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER | ORD/000017/2021-2022 | 141/CD | 06/07/2021 | 04/10/2021 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 19.25 | 0 | 0 | 1
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | Laying of Pipe Line & Construction Of 250 CUM OHR At BARA PINJARER JHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000400/2022-2023 | 1133/CD W | 03/11/2022 | 02/04/2023 | SUBHAS CHANDRA ROY | 98.43 | 0 | 0 | 60
8 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Pinjarirjhar water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000884/2023-2024 | 2459/NMD-II | 11/08/2023 | 10/09/2023 | M/S RATAN KUMAR DASGUPTA & CO. | 21.75 | 0 | 0 | 0
9 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA PINJARIRJHAR PIPED WATER SUPPLY SCHEME. | SM/13163 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000072/2025-2026 | 648/CD | 05/05/2025 | 03/08/2025 | Z STAR COMMOTRADE PVT LTD | 47.83 | 0 | 0 | 0
Total | [13 empty] | 740.91 | 0 | 0