## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Material Requisition To Resource Division |  |  | RTOR000128/2023-2024 | 234/CD | 27/04/2023 | 27/04/2023 | Resource Division | 14.03 | 0 | 0 | 0
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | QUOTATION FOR NEW SERVICE CONNECTION AT PUTIA BOGDABARI PH NO-I |  |  | BILL/00152/2023-2024 | BP-2023-24-126 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BOGDABARI PH NO-II |  |  | BILL/00153/2023-2024 | BP-2023-24-117 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.14 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Gap filling between pipe line related to Bhogdabri & Rajpur PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000539/2023-2024 | 628/CD | 11/03/2024 | 10/05/2024 | M/S MAA MANASA CONSTRUCTION CO. | 24.14 | 0 | 0 | 80
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BARA MARICHA & BHOGDABARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000567/2024-2025 | 2252/CD | 23/12/2024 | 21/02/2025 | AMBITIOUS ENTERPRISE | 43.46 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Execution of different works related to BHOGDABARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1112/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000566/2022-2023 | 1689/CD | 13/02/2023 | 29/12/2025 | AMBITIOUS ENTERPRISE | 360.81 | 0 | 0 | 70
7 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bara Bhogdabari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000977/2023-2024 | 2601/NMD-II | 24/08/2023 | 23/09/2023 | M/S KUNDU CONSTRUCTION | 20.19 | 0 | 0 | 60
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Execution of different works related to (within RAJPUR area) BHOGDABRI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000335/2023-2024 | 1324/CD | 24/11/2023 | 18/11/2025 | M/S MAA MANASA CONSTRUCTION CO. | 60.17 | 0 | 0 | 70
9 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Execution of different works related to BHOGDABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000419/2023-2024 | 1475/CD | 20/12/2023 | 09/12/2025 | AMBITIOUS ENTERPRISE | 46.15 | 0 | 0 | 60
10 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BHOGDABARI PIPED WATER SUPPLY SCHEME. | SM/13164 | New | Execution of different works related to BHOGDABRI PWSS (with in RAJPUR area) under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000012/2023-2024 | 394/CD | 23/05/2023 | 12/05/2025 | M/S MAA MANASA CONSTRUCTION CO. | 41.45 | 0 | 0 | 82
Total | [13 empty] | 612.59 | 0 | 0