## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Execution of different works related to PAKHIHAGA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 988/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000468/2022-2023 | 1519/CD | 19/01/2023 | 03/12/2025 | AKANSHA COMMERCIAL PVT. LTD. | 396.75 | 310.78 | 78.33 | 70
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pakhihaga water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000665/2023-2024 | 2021/NMD-II | 26/07/2023 | 06/05/2025 | TAPAN BISWAS | 19.77 | 17.8 | 90.04 | 100
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 177/CD | 27/04/2023 | 27/04/2023 | Resource Division | 20.95 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | QUOTATION FOR NSC AT PAKHIHAGA PH NI I |  |  | BILL/00524/2023-2024 | BP-2023-24-148 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | QUOTATION FOR NSC AT PAKHIHAGA PH NO II |  |  | BILL/00525/2023-2024 | BP-2023-24-149 | 01/06/2023 | 01/06/2023 | WBSEDCL | 1.11 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Execution of different works related to PAKHIHAGA PWSS under JAL JEEVAN MISSION DHT 1 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000478/2023-2024 | 281/CD | 09/02/2024 | 09/04/2024 | AKANSHA COMMERCIAL PVT. LTD. | 60.97 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | EXECUTION OF DIFFERENT WORKS RELATED TO PAKHIHAGA & JARABARI PRATHAM KHANDA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000561/2024-2025 | 2246/CD | 23/12/2024 | 16/02/2026 | MATARA CONSTRUCTION CO. | 32.27 | 5.31 | 16.45 | 70
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | PAKHIHAGA PIPED WATER SUPPLY SCHEME. | SM/13165 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000271/2025-2026 | 743/CD | 17/05/2025 | 15/08/2025 | M/S BADAL CH SAHA | 96.84 | 0 | 0 | 0
Total | [13 empty] | 20419.06 | 333.89 | 1.64