## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | Execution of different works related to BAROKODALI ZONE - I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1008/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000498/2022-2023 | 1563/CD | 24/01/2023 | 12/07/2025 | HARIDAS GHOSH | 377.55 | 205.34 | 54.39 | 69
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | Execution of different works related to BAROKODALI ZONE ii PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1007/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000499/2022-2023 | 1564/CD | 24/01/2023 | 23/06/2023 | GOUTAM KUMAR DAS | 293.01 | 249.24 | 85.06 | 90
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Barokodali water supply scheme, TW no I and II of Zone-I under Northern Mechanical Division-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000673/2023-2024 | 2058/NMD-II | 26/07/2023 | 31/01/2025 | DAS CONSTRUCTION | 20.8 | 19.55 | 94 | 100
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 220/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.89 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BAROKODALI PWSS (AUG) PH NO-I,Z-I |  |  | BILL/00027/2023-2024 | BP-2023-24-17 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BAROKODALI PWSS (AUG) PH NO-II,Z-I |  |  | BILL/00028/2023-2024 | BP-2023-24-24 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BARAKODALI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN TUFANGANJ-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13181 | Augmentation | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
Total | [13 empty] | 820.08 | 474.13 | 57.81