## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BAROKODALI PWSS (AUG) PH NO-II,Z-II |  |  | BILL/00030/2023-2024 | BP-2023-24-16 | 27/04/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BAROKODALI PWSS (AUG) PH NO-I,Z-II |  |  | BILL/00029/2023-2024 | BP-2023-24-25 | 27/04/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bara Kodali Water Supply Scheme TW No.- I & II of Zone-II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000073/2023-2024 | 1261/NMD-II | 05/07/2023 | 04/08/2023 | SUNLIT | 20.79 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Laying DI P/Line & other allied works related to BAROKODALI Z 2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000547/2023-2024 | 604/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 70.05 | 0 | 0 | 65
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Execution of different works related to BAROKODALI Z 1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000542/2023-2024 | 631/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 96.91 | 0 | 0 | 60
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Name of Work: Execution of different works related to Aug. of BAROKODALI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000264/2023-2024 | 1032/CD | 22/09/2023 | 21/11/2023 | GOUTAM KUMAR DAS | 96.51 | 33.31 | 34.51 | 80
Total | [13 empty] | 20075.57 | 33.31 | 0.17