## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bara Kodali Water Supply Scheme TW No.- I & II of Zone-II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000073/2023-2024 | 1261/NMD-II | 05/07/2023 | 04/08/2023 | SUNLIT | 20.79 | 13.29 | 63.93 | 40
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Name of Work: Execution of different works related to Aug. of BAROKODALI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000264/2023-2024 | 1032/CD | 22/09/2023 | 21/11/2023 | GOUTAM KUMAR DAS | 96.51 | 96.31 | 99.79 | 80
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BAROKODALI PWSS (AUG) PH NO-I,Z-II |  |  | BILL/00029/2023-2024 | BP-2023-24-25 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BAROKODALI PWSS (AUG) PH NO-II,Z-II |  |  | BILL/00030/2023-2024 | BP-2023-24-16 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Execution of different works related to BAROKODALI Z 1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000542/2023-2024 | 631/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 96.91 | 55.95 | 57.73 | 60
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Laying DI P/Line & other allied works related to BAROKODALI Z 2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000547/2023-2024 | 604/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 70.05 | 26.15 | 37.33 | 65
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BARA KODALI ZONE-II PWSS | SM/13182 | Augmentation | Hiring of Inspection Vehicle for Office of the Assistant Engineer, Coochbehar Mechanical Sub-Division , I.C.W JJM Works under Northern Mechanical Division -II , P.H.E Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000352/2024-2025 | 1854/CMSD | 27/05/2024 | 27/07/2024 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
Total | [13 empty] | 20076.27 | 191.7 | 0.95