## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | QUOTATION FOR NSC AT MAHISHCHARU P/H NO-I |  |  | BILL/01683/2023-2024 | BP-2023-24-306 | 08/09/2023 |  | WBSEDCL | 4.4 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | QUOTATION FOR NSC AT MAHISHCHARU P/H NO-II |  |  | BILL/01684/2023-2024 | BP-2023-24-307 | 08/09/2023 |  | WBSEDCL | 4.74 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Mahischaru water supply scheme, TW no I IIand III under NMD-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000635/2023-2024 | 1933NMD-II | 21/07/2023 | 20/08/2023 | B.B CONCERNED | 33.16 | 13.93 | 42 | 40
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | VEHICLE BILL FOR AE/SADAR (JUN&JULY,2023) |  |  | BILL/01091/2023-2024 | BP-628 | 13/10/2023 |  | PARAUDDIN MIAH | 0.35 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | VEHICLE FOR COB DIVN. (AUG,2023) |  |  | BILL/01092/2023-2024 | BP-629 | 13/10/2023 |  | PARAUDDIN MIAH | 0.18 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | VEHICLE BILL FOR AE/RWS (SEPT,2023) |  |  | BILL/01090/2023-2024 | BP-627 | 13/10/2023 |  | AJAD HOSSAIN | 0.21 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | EXECUTION OF MDIFFERENT WORKS AT DEBOTTAR BAKSHIGANJ PWSS |  |  | BILL/01107/2023-2024 | BP-546 | 07/10/2023 |  | DAS ENTERPRISE | 35.11 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | Execution of different works related to MAHISHCHARU PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000425/2023-2024 | 1481/CD | 20/12/2023 | 18/02/2024 | JAL PRAVAHIKA PRIVATE LIMITED | 93.19 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 81/CD | 11/01/2024 |  | Resource Division | 15.64 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | FUEL BILL |  |  | BILL/02021/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 0.99 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | Execution of different works related to MAHISHCHARU PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1207/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000580/2022-2023 | 1770/CD | 02/03/2023 | 30/07/2023 | JAL PRAVAHIKA PVT. LTD. | 528.53 | 140 | 26.49 | 85
13 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | MAHISHCHARU PIPED WATER SUPPLY SCHEME. | SM/13207 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20553.33 | 153.93 | 0.75