## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 68/CD | 11/01/2024 | 11/01/2024 | Resource Division | 17.2 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT KHESTI TW I. |  |  | BILL/00978/2024-2025 | BP-283/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 4.42 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | Execution of different works related to KSHETI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1240/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000545/2022-2023 | 1785/CD | 02/03/2023 | 03/09/2025 | GHOSH AND SAHA CONSTRUCTION | 580.19 | 392.53 | 67.66 | 50
4 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Ksheti water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000791/2023-2024 | 2361/NMD-II | 07/08/2023 | 06/09/2023 | MENAKA ENTERPRISE | 22.88 | 19.21 | 84 | 40
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 229.07 | 1.16 | 20
6 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | Laying DI P/Line & other allied works related to KSHETI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000589/2023-2024 | 626/CD | 11/03/2024 | 12/01/2025 | GHOSH AND SAHA CONSTRUCTION | 59.57 | 49.54 | 83.17 | 30
7 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | KSHETI PIPED WATER SUPPLY SCHEME. | SM/13208 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (with CHHITRI BARI & ANGARKATA PARADUBI area) KSHETI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000615/2024-2025 | 2316/CD | 23/12/2024 | 21/02/2025 | GHOSH AND SAHA CONSTRUCTION | 96.3 | 0 | 0 | 0
Total | [13 empty] | 20569.85 | 690.35 | 3.36