## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-II Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000389/2023-2024 | 1092/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
2 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000388/2023-2024 | 1091/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
3 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000391/2023-2024 | 1094/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
4 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KHENGCHI PH NO-I |  |  | BILL/00154/2023-2024 | BP-2023-24-110 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
5 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KHENGCHI PH NO-II |  |  | BILL/00155/2023-2024 | BP-2023-24-111 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Execution of different works related to KHENGCHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000535/2022-2023 | 1611/CD | 03/02/2023 | 03/07/2023 | ASHIM KUMAR CHAKRABORTY | 325.25 | 324.67 | 99.82 | 10
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Execution of different works related to KHENGCHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000126/2023-2024 | 669/CD | 14/07/2023 | 11/12/2023 | ASHIM KUMAR CHAKRABORTY | 78.79 | 71.29 | 90.48 | 92
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Execution of different works related to BARA DHAPERCHATRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000725/2022-2023 | 1654 | 10/02/2023 | 11/04/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 23.41 | 13 | 55.53 | 100
9 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Khengchi water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000666/2023-2024 | 2039/NMD-II | 26/07/2023 | 25/08/2023 | M/S DILIP MITRA | 19.78 | 19.43 | 98.24 | 100
10 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000390/2023-2024 | 1093/CD | 29/09/2023 | 29/12/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
11 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | EXECUTION OF DIFFERENT WORK AT JIRAN PUR PWSS |  |  | BILL/02072/2023-2024 | BP-1227-P1 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 109.82 | 0 | 0 | 0
12 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | Execution of different works (WITHIN BALASI AREA) related to KHENGCHI PWSS under JAL JEEVAN MISSION |  |  | ORD/000809/2023-2024 | 276/CD | 09/02/2024 | 09/04/2024 | ASHIM KUMAR CHAKRABORTY | 45.66 | 0 | 0 | 0
13 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | KHENGCHI PIPED WATER SUPPLY SCHEME. | SM/13209 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000288/2025-2026 | 797/CD | 23/05/2025 | 21/08/2025 | MA MAHAMAYA UNP. CO-OP LABOUR CONT & CONT SOCITY LTD. | 24 | 0 | 0 | 0
Total | [13 empty] | 632.77 | 432.33 | 68.32