## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Gorbhanga water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/001026/2023-2024 | 2659/NMD-II | 04/09/2023 | 04/10/2023 | UTTAM PAUL | 19.62 | 0 | 0 | 0
2 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | Execution of different works related to GORBHANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000558/2023-2024 | 603/CD | 11/03/2024 | 06/03/2025 | SUPER -TECH ENGINEERS'CO-OPERATIVE SOCIETY LIMITED | 38.85 | 6.99 | 17.99 | 30
3 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | QUOTATION FOR NSC AT GORBHANGA TW NO I |  |  | BILL/02467/2023-2024 | BP-2023-24-536 | 17/01/2024 | 17/01/2024 | WBSEDCL | 7.65 | 0 | 0 | 0
4 | COOCHBEHAR | Tufanganj-II | Northern Mechanical Division II | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | QUOTATION FOR NSC AT GORBHANGA TW NO II |  |  | BILL/02468/2023-2024 | BP-2023-24-537 | 17/01/2024 | 17/01/2024 | WBSEDCL | 4.79 | 0 | 0 | 0
5 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TATERKUTHI KHAGRIBARI GORBHANGA & FALIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000557/2024-2025 | 2242/CD | 23/12/2024 | 21/02/2025 | HARIDAS GHOSH | 65.94 | 1.88 | 2.84 | 60
6 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000275/2025-2026 | 739/CD | 17/05/2025 | 12/05/2026 | DAS ENTERPRISE | 37.76 | 0 | 0 | 70
7 | COOCHBEHAR | Tufanganj-II | Coochbehar Division | GORBHANGA PIPED WATER SUPPLY SCHEME. | SM/13210 | New | Execution of different works related to GORBHANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1291/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000600/2022-2023 | 1906/CD | 17/03/2023 | 31/03/2025 | SUPER TECH ENGINEERS CO- OPERATIVE SPOCY.LTD | 217.03 | 130.43 | 60.1 | 95
Total | [13 empty] | 391.65 | 139.3 | 35.57