## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - II | Coochbehar Division | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 1346/CD | 19/12/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - II | Coochbehar Division | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | Providing FHTC & New UPVC/DI Pipe line with other allied works (PART ¿B) at SALMARA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000367/2021-2022 | 1270/CD | 09/02/2022 | 02/10/2023 | TAPAN CHANDA | 85.55 | 2.41 | 2.82 | 1
3 | COOCHBEHAR | Dinhata - II | Coochbehar Division | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | Providing FHTC Pump House & Boundary wall New UPVC/DI Pipe line with other allied works (PART -A) at SALMARA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000469/2021-2022 | 1615/CD | 25/03/2022 | 23/07/2022 | TAPAN CHANDA | 134.12 | 0.79 | 0.59 | 1
4 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Choto Garoljhora water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/001027/2023-2024 | 2661/NMD-II | 04/09/2023 | 04/10/2023 | MUSTAFI CONCERN | 19.79 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | QUOTATION FOR NSC AT CHOTO GAROLJHORA TW NO-I |  |  | BILL/01801/2023-2024 | BP-2023-24-335 | 27/09/2023 |  | WBSEDCL | 2.28 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | QUOTATION FOR NSC AT CHOTO GAROLJHORA TW NO-II |  |  | BILL/01800/2023-2024 | BP-2023-24-336 | 27/09/2023 |  | WBSEDCL | 9.03 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - II | Coochbehar Division | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | Execution of different works related to CHOTO GAROLJHORA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1110/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000564/2022-2023 | 1692/CD | 13/02/2023 | 13/07/2023 | S.G ENTERPRISE | 206.36 | 86.12 | 41.73 | 49
8 | COOCHBEHAR | Dinhata - II | Coochbehar Division | CHOTO GAROLJHORA PIPED WATER SUPPLY SCHEME. | SM/13211 | New | HIRING VEHICLE FOR AE/SD |  |  | BILL/00488/2024-2025 | null | 01/06/2024 |  | PARAUDDIN MIA | 0.55 | 0 | 0 | 0
Total | [13 empty] | 519.28 | 89.32 | 17.2