## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Execution of different works related to CHHOTA KESHARI BARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000524/2022-2023 | 1679/CD | 13/02/2023 | 28/09/2025 | M/S KARNATAKA CONSTRUCTION COMPANY | 338.9 | 282.71 | 83.42 | 80
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Chhota Kesharibari water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000874/2023-2024 | 2458/NMD-II | 11/08/2023 | 10/09/2023 | S.P ENTERPRISE (SLG) | 21.62 | 0 | 0 | 60
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Execution of different works related to CHHOTO KESARIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000472/2023-2024 | 274/CD | 09/02/2024 | 16/10/2025 | M/S KARNATAKA CONSTRUCTION COMPANY | 82.06 | 54.59 | 66.53 | 85
4 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | EXECUTION OF DIFFERENT WORK AT CHOTO KESHARI BARI PWSS |  |  | BILL/02038/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 0 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHOTO KESARIBARI TW I. |  |  | BILL/00640/2024-2025 | BP-209/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 7.74 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHHOTA KESHARIBARI TW NO II. |  |  | BILL/00341/2024-2025 | BP-113/24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL | 10.23 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | EXECUTION OF DIFFERENT WORKS (within CHHOTA KESHARI BAR & MAHISHCHARU area) RELATED TO SARAHATI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000660/2024-2025 | 89/CD | 17/01/2025 | 13/03/2026 | PARTHA DAS | 92.45 | 0 | 0 | 30
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000256/2025-2026 | 754/CD | 17/05/2025 | 15/08/2025 | M/S T M CONSTRUCTION | 95.38 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000292/2025-2026 | 1422/CD | 11/08/2025 | 09/12/2025 | M/S SURAJIT MAJUMDER | 29.52 | 0 | 0 | 50
Total | [13 empty] | 20467.19 | 337.3 | 1.65