## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Chhota Kesharibari water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000874/2023-2024 | 2458/NMD-II | 11/08/2023 | 10/09/2023 | S.P ENTERPRISE (SLG) | 21.62 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | EXECUTION OF DIFFERENT WORK AT CHOTO KESHARI BARI PWSS |  |  | BILL/02038/2023-2024 | null | 01/03/2024 |  | A.O BSNL | 0 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHHOTA KESHARIBARI TW NO II. |  |  | BILL/00341/2024-2025 | BP-113/24-25 | 21/05/2024 |  | WBSEDCL | 10.23 | 0 | 0 | null
4 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Execution of different works related to CHHOTA KESHARI BARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000524/2022-2023 | 1679/CD | 13/02/2023 | 13/07/2023 | M/S KARNATAKA CONSTRUCTION COMPANY | 338.9 | 137.45 | 40.56 | 80
5 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHOTO KESARIBARI TW I. |  |  | BILL/00640/2024-2025 | BP-209/24-25 | 15/07/2024 |  | WBSEDCL | 7.74 | 0 | 0 | null
6 | COOCHBEHAR | Mathabhanga - I | Northern Mechanical Division II | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT CHOTO KESARIBARI TW I. |  |  | BILL/00640/2024-2025 | BP-209/24-25 | 15/07/2024 |  | WBSEDCL | 7.74 | 0 | 0 | null
7 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - I | Coochbehar Division | CHHOTA KESHARI BARI PIPED WATER SUPPLY SCHEME. | SM/13212 | New | Execution of different works related to CHHOTO KESARIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000472/2023-2024 | 274/CD | 09/02/2024 | 09/04/2024 | M/S KARNATAKA CONSTRUCTION COMPANY | 82.06 | 0 | 0 | 85
Total | [13 empty] | 20257.58 | 137.45 | 0.68