## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | SUPPLY OF FUEL FOR TFG SUB DIVISION, PHED |  |  | BILL/00563/2023-2024 | BP-175 | 31/05/2023 |  | SUCHITRO FUEL STATION | 0.82 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | VEHICLE FOR AE/SD |  |  | BILL/00566/2023-2024 | BP-41 | 19/04/2023 |  | PARAUDDIN MIAH | 0.18 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | VEHICLE AE/RWS |  |  | BILL/00565/2023-2024 | BP-42 | 19/04/2023 |  | AJAD HOSSAIN | 0.18 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | EXECUTIION OF DIFFERENT TYPE OF WORK AT STABHANDARI PWSS |  |  | BILL/00505/2023-2024 | BP-130-P1 | 19/05/2023 |  | SWAPAN KR.SARKAR | 0 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | SINKING T/WELL AT CHHATOA PWSS |  |  | BILL/00509/2023-2024 | BP-91-P2 | 04/05/2023 |  | AUXILIARY TUBEWELL DRILLERS | 0 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | EXC. OF DIFFT. WORKS AT JHINGAPUNI PWSS |  |  | BILL/00512/2023-2024 | BP-173-P2 | 31/05/2023 |  | MATRI ENTERPRISEES | 0.04 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | EXC. OF DIFFT. OF WORK AT PUTIA BAKSHIBAS PWSS |  |  | BILL/00517/2023-2024 | BP-172-P2 | 31/05/2023 |  | NABIN DEBNATH | 0.03 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | UPLOAD CHRGES FOR FHTC |  |  | BILL/00677/2023-2024 | BP-338 | 20/07/2023 |  | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | UPLOAD CHARGES OF FHTC |  |  | BILL/00672/2023-2024 | BP-335 | 20/07/2023 |  | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | upload charges for fhtc |  |  | BILL/00673/2023-2024 | BP-339 | 20/07/2023 |  | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | UPLOAD CHARGES FOR FHTC |  |  | BILL/00676/2023-2024 | BP-337 | 20/07/2023 |  | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | HIRING OF VEHICLE FO AE/SD |  |  | BILL/00665/2023-2024 | BP-266 | 11/07/2023 |  | PARAUDDIN MIAH | 0.38 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | HIRING VEHICLE FOR AE/RWS |  |  | BILL/00678/2023-2024 | BP-346 | 20/07/2023 |  | AJAD HOSSAIN | 0.54 | 0 | 0 | 0
14 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | ELECTRIC QUOTATION BILL FOR NSC AT CHHITRIBARI TW NO.I |  |  | BILL/02315/2023-2024 | BP-2023-24-506 | 05/01/2024 |  | WBSEDCL | 1.05 | 0 | 0 | 0
15 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | ELECTRIC QUOTATION BILL FOR NSC AT CHHITRIBARI TW NO.II |  |  | BILL/02316/2023-2024 | BP-2023-24-507 | 05/01/2024 |  | WBSEDCL | 1.05 | 0 | 0 | 0
16 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | Execution of different works related to CHHITRI BARI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 985/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000465/2022-2023 | 1516/CD | 19/01/2023 | 18/06/2023 | M/S. NITYAGOPAL BANIK | 305.58 | 165.93 | 54.3 | 32
17 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | SHIFTING OF EXISTING LT OH LINE AT CHHITRIBARI PWSS FOR SAFETY OF THE PUMP HOUSE, UNDER DOLONGMORE CCC. |  |  | BILL/00052/2024-2025 | BP-12/24-25 | 08/04/2024 |  | WBSEDCL | 0.66 | 0 | 0 | null
18 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | SHIFTING OF EXISTING LT OH LINE AT CHHITRIBARI PWSS FOR SAFETY OF THE PUMP HOUSE, UNDER DOLONGMORE CCC. |  |  | BILL/00052/2024-2025 | BP-12/24-25 | 08/04/2024 |  | WBSEDCL | 0.66 | 0 | 0 | null
19 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for CHHITRI BARI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000668/2023-2024 | 2064/NMD-II | 26/07/2023 | 25/08/2023 | M/S MATRI CONSTRUCTION | 21.12 | 0 | 0 | 40
20 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | CHHITRI BARI PIPED WATER SUPPLY SCHEME. | SM/13213 | New | Execution of different works related to CHHITRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000421/2023-2024 | 1477/CD | 20/12/2023 | 18/02/2024 | SANJAY MANDAL | 50.88 | 17.03 | 33.48 | 66
Total | [13 empty] | 387.07 | 182.96 | 47.27