## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 100/CD | 26/04/2023 | 26/04/2023 | Resource Division | 29.4 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | New service connection for BRAHMATTAR KASALDANGA , ZONE-I, PH-II |  |  | BILL/02070/2023-2024 | BP-2023-24-435 | 05/12/2023 | 05/12/2023 | WBSEDCL | 9.48 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BRAHMOTTAR KASHALDANGA TW NO-I |  |  | BILL/00160/2023-2024 | BP-2023-24-125 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | QUOTATION FOR INFRASTRUCTIRE DEV. COST FOR EFFECTING 01 NO PHE VIDE APPLICATION NO -4003137809 AT BRAMHATTAR KASHALDANGA. |  |  | BILL/01007/2023-2024 | BP-2023-24-216 | 13/07/2023 | 13/07/2023 | WBSEDCL | 8.85 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | QUOTATION FOR INFRASTRUCTIRE DEV. COST FOR EFFECTING 01 NO PHE VIDE APPLICATION NO -4003137790 AT BRAMHATTAR KASHALDANGA. |  |  | BILL/01006/2023-2024 | BP-2023-24-217 | 13/07/2023 | 13/07/2023 | WBSEDCL | 18.38 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BRAHMOTTAR KASHALDANGA TW NO-II |  |  | BILL/00161/2023-2024 | BP-2023-24-124 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | New service connection for BRAHMATTAR KASHALDANGA PWSS, PH-I |  |  | BILL/02066/2023-2024 | BP-2023-24-436 | 05/12/2023 | 05/12/2023 | WBSEDCL | 6.44 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Execution of different works related to BRAHMATTAR KASALDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000345/2023-2024 | 1329/CD | 24/11/2023 | 23/01/2024 | GOUTAM KUMAR DAS | 22.79 | 0 | 0 | 98
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Execution of different works related to BRAHMOTTAR KASAL DANGA Z2 PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 981/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000461/2022-2023 | 1512/CD | 19/01/2023 | 18/06/2023 | SWAPAN KUMAR ROY | 346.55 | 0 | 0 | 49
10 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Brahmottar Kasal Danga water supply scheme, TW no I , II, III & IV under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000755/2023-2024 | 2275/NMD-II | 31/07/2023 | 30/08/2023 | ALPHA ENTERPRISE | 39.54 | 0 | 0 | 100
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Extension Work for Uploading charges of https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) |  | Junior Engineer, Head Quarter | ORD/000500/2023-2024 | 1541/CD | 29/12/2023 | 31/12/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
12 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Extension Work for Uploading charges of https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-C) |  | Junior Engineer, Head Quarter | ORD/000499/2023-2024 | 1540/CD | 29/12/2023 | 29/02/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
13 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Extension Work for Uploading charges of https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) |  | Junior Engineer, Head Quarter | ORD/000501/2023-2024 | 1542/CD | 29/12/2023 | 29/02/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
14 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Extension Work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-A) |  | Junior Engineer, Head Quarter | ORD/000497/2023-2024 | 1538/CD | 29/12/2023 | 29/02/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
15 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Extension Work for Uploading charges of https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) |  | Junior Engineer, Head Quarter | ORD/000502/2023-2024 | 1544/CD | 29/12/2023 | 29/02/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
16 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Extension Work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-B) |  | Junior Engineer, Head Quarter | ORD/000498/2023-2024 | 1539/CD | 29/12/2023 | 29/02/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
17 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 65/CD | 11/01/2024 | 11/01/2024 | Resource Division | 17.55 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | HIRING OF VEHICLE FOR AE/TFG |  |  | BILL/00485/2024-2025 | BP-207 | 31/07/2024 | 31/07/2024 | NABIN DEBNATH | 1.06 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | HIRING VEHICLE FOR AE/MTB |  |  | BILL/00487/2024-2025 | BP-205 | 31/07/2024 | 31/07/2024 | NABIN DEBNATH | 1.07 | 0 | 0 | 0
20 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Execution of different works related to BRAHMOTTAR KASALDANGA Z-I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000524/2023-2024 | 322/CD | 09/02/2024 | 12/12/2025 | SWAPAN KUMAR ROY | 55.27 | 0 | 0 | 30
21 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Execution of different works related (Within area of DEWANHAT) to PHALIMARI & adjacent of MOAMARI & BRAHMOTTAR KASAL DANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000067/2024-2025 | 1324/CD | 19/07/2024 | 20/07/2025 | DAS ENTERPRISE | 45.49 | 0 | 0 | 30
22 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000127/2025-2026 | 1423/CD | 11/08/2025 | 09/11/2025 | NARAYAN CHANDRA BANIK | 22.06 | 0 | 0 | 0
23 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000128/2025-2026 | 1424/CD | 11/08/2025 | 09/11/2025 | NARAYAN CHANDRA BANIK | 22.32 | 0 | 0 | 0
24 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | BRAHMOTTAR KASAL DANGA PIPED WATER SUPPLY SCHEME. | SM/13214 | New | Execution of different works related to BRAHMOTTAR KASAL DANGA Z1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 999/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000486/2022-2023 | 1551/CD | 24/01/2023 | 01/04/2025 | SWAPAN KUMAR ROY | 317.38 | 0 | 0 | 60
Total | [13 empty] | 971.56 | 0 | 0