## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 132/CD | 27/04/2023 | 27/04/2023 | Resource Division | 22.41 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Bijlichatka water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P,Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000847/2023-2024 | 2427/NMD-II | 10/08/2023 | 09/09/2023 | KARMAKAR CONSTRUCTION | 21.59 | 20.21 | 93.65 | 80
3 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Material Requisition To Resource Division |  |  | RTOR000194/2023-2024 | 89/CD | 11/01/2024 | 11/01/2024 | Resource Division | 13.79 | 0 | 0 | 0
4 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BIJLICHATKA TW NO. I |  |  | BILL/02612/2023-2024 | BP-2023-24-575 | 01/02/2024 | 01/02/2024 | WBSEDCL | 8.45 | 0 | 0 | 0
5 | COOCHBEHAR | Sitai | Northern Mechanical Division II | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BIJLICHATKA TW NO. II. |  |  | BILL/02613/2023-2024 | BP-2023-24-576 | 01/02/2024 | 01/02/2024 | WBSEDCL | 7.78 | 0 | 0 | 0
6 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | EXECUTION OF DIFFERENT WORKS RELATED TO KONACHATRA ZONE-II & BIJLICHATKA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000538/2024-2025 | 2222/CD | 23/12/2024 | 18/12/2025 | GEETA CONSTRUCTION | 54.42 | 0 | 0 | 75
8 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | HORDING/ SIGN BOARD FOR IEC CAMPAINING AT GP OFFICE / BLOCK OFFICE & DIFFERENT HEALTH CENTERS UNDER COOCH BEHAR DIVISION , PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000704/2024-2025 | 2326/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 48.03 | 0 | 0 | 100
9 | COOCHBEHAR | Sitai | Coochbehar Division | BIJLICHATKA PIPED WATER SUPPLY SCHEME. | SM/13215 | New | Execution of different works related to BIJLICHATKA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 976/1-5/NBC-1; DT: 19-01-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000455/2022-2023 | 1506/CD | 19/01/2023 | 13/04/2026 | GEETA CONSTRUCTION | 400.44 | 182.56 | 45.59 | 90
Total | [13 empty] | 20366.2 | 202.78 | 1